## Read Me
CBMS — Agile Backlog & Work Breakdown Structure
Centralized Barangay Management System · 12-month delivery plan · Epic → Feature → User Story → Task
PURPOSE
A single, filterable backlog for one year of CBMS delivery, broken down four levels deep. Every item traces from a business Epic down to an engineering Task.
HOW THE HIERARCHY WORKS
Epic | A large body of value delivered over one or more quarters (e.g. the Barangay E-Wallet). Points roll up from its stories.
Feature | A coherent capability inside an Epic that can be demoed on its own (e.g. maker–checker disbursement).
User Story | A slice of value stated from a user's point of view, with acceptance criteria. This is the ONLY level that carries story points.
Task | The engineering work to deliver a story. Estimated in hours, not points.
HOW TO READ THE BACKLOG SHEET
Story Points | Fibonacci (1,2,3,5,8,13) on User Stories only. Epic and Feature rows are SUMIFS rollups — never type over them.
Est. Hours | On Task rows only. Epic/Feature/Story rows roll these up.
Sprint | S01–S26. Two-week sprints across 12 months.
PI | Program Increment (quarter). PI-1 through PI-4.
MoSCoW | Must / Should / Could / Won't (this release).
Group | Marks whether the work mirrors a DILG LGUSS-BIMS sub-system (BIMS-parity) or is CBMS-exclusive whitespace.
Status | To Do / In Progress / In Review / Done / Blocked. Update this column as work proceeds.
WHICH CELLS YOU EDIT
Blue text = you fill these in (Status, Owner, Sprint, and estimates you wish to change).
Black text = formulas. Do not overwrite; they recalculate from the rows beneath.
PRODUCT CONTEXT
CBMS is a companion to DILG's LGUSS-BIMS, which is mandatory for all barangays under Memorandum Circular No. 2025-104.
CBMS never replaces BIMS. Group A epics mirror BIMS sub-systems (BIPS, BCIS, KPISBH, BAMS, BDRIS, BGADPBMS, BORIS, BFMS) and defer to it as the system of record.
Group B epics — the e-wallet, the AI layer and resident self-service — are capabilities BIMS does not have at all.
ASSUMPTIONS BEHIND THE PLAN
Team | Approximately 29 people across 3 delivery squads plus a platform group. See the 'Team & Capacity' sheet.
Sprints | 26 two-week sprints. Sprint 26 is a hardening and release sprint, deliberately under-loaded.
Velocity | Backlog-facing capacity of about 26 points per sprint once ramped, giving roughly 75% planned load.
Point size | One story point is estimated at roughly 2.8 hours of focused engineering in this plan.
Source | Scope is derived from the CBMS build specification (OPUS-BUILD-PROMPT.md) and the delivered codebase.
Caveat | Estimates are planning figures for scoping and sequencing, not a commercial commitment. Re-estimate at sprint planning.
READ THIS BEFORE SIZING THE TEAM
This backlog sizes DEFINED PRODUCT SCOPE only. It deliberately excludes discovery, rework, code review, ceremonies, environment problems, production support, field deployment, training and the barangay-by-barangay rollout — which in a programme of this kind consume the majority of a team's year.
So the total task hours here are much smaller than the total hours a 29-person team works in twelve months. That is expected and intentional. Do not use this workbook on its own to justify headcount or a budget; pair it with the delivery and deployment plan.

## Backlog
CBMS Delivery Backlog — Work Breakdown Structure
Epic → Feature → User Story → Task. Story points live on User Stories; Epic and Feature totals are formulas.
Level | ID | Parent ID | Epic ID | Feature ID | Title | Description / Acceptance Criteria | Group | Squad | MoSCoW | Story Points | Est. Hours | Sprint | PI | Status | Owner | Notes / Dependencies
Epic | E01 |  | E01 |  | Platform Foundation & Multi-Tenancy | The monorepo, database, tenancy model and shared packages every other epic builds on. | Platform | Platform | Must | 45 | 129 |  | PI-1 (Q1) | To Do |  | Critical path — blocks all other epics.
Feature | F01.1 | E01 | E01 | F01.1 | Monorepo, CI/CD and local environment | A new engineer can clone and run the full stack in under 15 minutes. | Platform | Platform | Must | 13 | 40 |  | PI-1 (Q1) | To Do
User Story | US01.1.1 | F01.1 | E01 | F01.1 | As a developer, I can start the whole stack with one command | GIVEN a clean clone WHEN I run docker compose up and pnpm setup THEN Postgres, MailHog and MinIO start and all apps boot without manual steps. | Platform | Platform | Must | 5 | 18 | S01 | PI-1 (Q1) | To Do
Task | T01.1.1.1 | US01.1.1 | E01 | F01.1 | Scaffold pnpm workspace + Turborepo pipeline |  | Platform | Platform |  |  | 6 | S01 | PI-1 (Q1) | To Do
Task | T01.1.1.2 | US01.1.1 | E01 | F01.1 | Author docker-compose (Postgres, MailHog, MinIO) with healthchecks |  | Platform | Platform |  |  | 4 | S01 | PI-1 (Q1) | To Do
Task | T01.1.1.3 | US01.1.1 | E01 | F01.1 | Create .env.example and env loading via dotenv-cli |  | Platform | Platform |  |  | 3 | S01 | PI-1 (Q1) | To Do
Task | T01.1.1.4 | US01.1.1 | E01 | F01.1 | Write root scripts: setup, dev, seed, db:push |  | Platform | Platform |  |  | 3 | S01 | PI-1 (Q1) | To Do
Task | T01.1.1.5 | US01.1.1 | E01 | F01.1 | Document the 15-minute quick start in README |  | Platform | Platform |  |  | 2 | S01 | PI-1 (Q1) | To Do
User Story | US01.1.2 | F01.1 | E01 | F01.1 | As a team, we get automated lint, typecheck, test and build on every push | GIVEN a pull request WHEN CI runs THEN lint, typecheck, unit tests and build all execute and block merge on failure. | Platform | Platform | Must | 5 | 12 | S02 | PI-1 (Q1) | To Do
Task | T01.1.2.1 | US01.1.2 | E01 | F01.1 | Configure CI workflow with pnpm cache |  | Platform | Platform |  |  | 5 | S02 | PI-1 (Q1) | To Do
Task | T01.1.2.2 | US01.1.2 | E01 | F01.1 | Add turbo lint/typecheck/test/build tasks |  | Platform | Platform |  |  | 4 | S02 | PI-1 (Q1) | To Do
Task | T01.1.2.3 | US01.1.2 | E01 | F01.1 | Add branch protection and required checks |  | Platform | Platform |  |  | 2 | S02 | PI-1 (Q1) | To Do
Task | T01.1.2.4 | US01.1.2 | E01 | F01.1 | Publish build status badge |  | Platform | Platform |  |  | 1 | S02 | PI-1 (Q1) | To Do
User Story | US01.1.3 | F01.1 | E01 | F01.1 | As a developer, shared code lives in versioned workspace packages | GIVEN shared logic WHEN it is imported THEN it resolves from @cbms/* with no relative cross-app paths. | Platform | Platform | Must | 3 | 10 | S02 | PI-1 (Q1) | To Do
Task | T01.1.3.1 | US01.1.3 | E01 | F01.1 | Create packages: db, rbac, auth, payments, ui, api-client |  | Platform | Platform |  |  | 5 | S02 | PI-1 (Q1) | To Do
Task | T01.1.3.2 | US01.1.3 | E01 | F01.1 | Set ESM exports + type module on every package |  | Platform | Platform |  |  | 3 | S02 | PI-1 (Q1) | To Do
Task | T01.1.3.3 | US01.1.3 | E01 | F01.1 | Add tsconfig.base and per-package tsconfig |  | Platform | Platform |  |  | 2 | S02 | PI-1 (Q1) | To Do
Feature | F01.2 | E01 | E01 | F01.2 | Data model and PSGC tenancy backbone | Region -> Province -> City/Municipality -> Barangay, with row-level tenant scoping. | Platform | Platform | Must | 24 | 70 |  | PI-1 (Q1) | To Do
User Story | US01.2.1 | F01.2 | E01 | F01.2 | As an architect, the schema models every CBMS module | GIVEN the Prisma schema WHEN validated THEN all Group A and Group B entities exist with correct relations and indexes. | Platform | Platform | Must | 13 | 36 | S01 | PI-1 (Q1) | To Do
Task | T01.2.1.1 | US01.2.1 | E01 | F01.2 | Model core: PSGC, Barangay, User, Role, Permission, AuditLog, ConsentRecord |  | Platform | Platform |  |  | 8 | S01 | PI-1 (Q1) | To Do
Task | T01.2.1.2 | US01.2.1 | E01 | F01.2 | Model Group A entities (registry, issuance, KP, assets, disaster, governance, finance) |  | Platform | Platform |  |  | 12 | S01 | PI-1 (Q1) | To Do
Task | T01.2.1.3 | US01.2.1 | E01 | F01.2 | Model Group B entities (wallet, AI, resident self-service) |  | Platform | Platform |  |  | 10 | S01 | PI-1 (Q1) | To Do
Task | T01.2.1.4 | US01.2.1 | E01 | F01.2 | Add indexes for tenant + status query paths |  | Platform | Platform |  |  | 4 | S01 | PI-1 (Q1) | To Do
Task | T01.2.1.5 | US01.2.1 | E01 | F01.2 | Run prisma validate and db push against Postgres |  | Platform | Platform |  |  | 2 | S01 | PI-1 (Q1) | To Do
User Story | US01.2.2 | F01.2 | E01 | F01.2 | As a security lead, every query is constrained to the caller's barangay | GIVEN a barangay-scoped user WHEN any query runs THEN a barangayId filter is injected server-side and cross-tenant writes throw. | Platform | Platform | Must | 8 | 22 | S03 | PI-1 (Q1) | To Do
Task | T01.2.2.1 | US01.2.2 | E01 | F01.2 | Implement createScopedClient with Prisma $extends |  | Platform | Platform |  |  | 8 | S03 | PI-1 (Q1) | To Do
Task | T01.2.2.2 | US01.2.2 | E01 | F01.2 | Handle findUnique degradation to findFirst under scope |  | Platform | Platform |  |  | 3 | S03 | PI-1 (Q1) | To Do
Task | T01.2.2.3 | US01.2.2 | E01 | F01.2 | Block cross-tenant create/createMany/update/delete |  | Platform | Platform |  |  | 4 | S03 | PI-1 (Q1) | To Do
Task | T01.2.2.4 | US01.2.2 | E01 | F01.2 | Add aggregates-only mode for the DILG viewer role |  | Platform | Platform |  |  | 3 | S03 | PI-1 (Q1) | To Do
Task | T01.2.2.5 | US01.2.2 | E01 | F01.2 | Write cross-tenant leak tests |  | Platform | Platform |  |  | 4 | S03 | PI-1 (Q1) | To Do
User Story | US01.2.3 | F01.2 | E01 | F01.2 | As a treasurer, money is never subject to floating-point error | GIVEN any peso amount WHEN stored or computed THEN it is BigInt centavos and money(0.1)+money(0.2) equals money(0.3). | Platform | Platform | Must | 3 | 12 | S03 | PI-1 (Q1) | To Do
Task | T01.2.3.1 | US01.2.3 | E01 | F01.2 | Implement money/centavos/formatPeso helpers |  | Platform | Platform |  |  | 4 | S03 | PI-1 (Q1) | To Do
Task | T01.2.3.2 | US01.2.3 | E01 | F01.2 | Implement splitEvenly with remainder preservation |  | Platform | Platform |  |  | 3 | S03 | PI-1 (Q1) | To Do
Task | T01.2.3.3 | US01.2.3 | E01 | F01.2 | Implement bpsFee with half-up rounding |  | Platform | Platform |  |  | 2 | S03 | PI-1 (Q1) | To Do
Task | T01.2.3.4 | US01.2.3 | E01 | F01.2 | Unit-test the float trap and split conservation |  | Platform | Platform |  |  | 3 | S03 | PI-1 (Q1) | To Do
Feature | F01.3 | E01 | E01 | F01.3 | Seed data and demo environment | A realistic, synthetic dataset that makes every screen demonstrable. | Platform | Platform | Must | 8 | 19 |  | PI-1 (Q1) | To Do
User Story | US01.3.1 | F01.3 | E01 | F01.3 | As a demo lead, the system seeds a believable barangay dataset | GIVEN pnpm seed WHEN it completes THEN 16 Marikina barangays, 500+ inhabitants, households, wallets and transactions exist with synthetic Filipino data. | Platform | Platform | Must | 8 | 19 | S04 | PI-1 (Q1) | To Do
Task | T01.3.1.1 | US01.3.1 | E01 | F01.3 | Build deterministic RNG and Filipino name/address pools |  | Platform | Platform |  |  | 5 | S04 | PI-1 (Q1) | To Do
Task | T01.3.1.2 | US01.3.1 | E01 | F01.3 | Seed PSGC and the 16 Marikina barangays |  | Platform | Platform |  |  | 3 | S04 | PI-1 (Q1) | To Do
Task | T01.3.1.3 | US01.3.1 | E01 | F01.3 | Seed households, inhabitants and sectoral flags |  | Platform | Platform |  |  | 6 | S04 | PI-1 (Q1) | To Do
Task | T01.3.1.4 | US01.3.1 | E01 | F01.3 | Seed consent records per household |  | Platform | Platform |  |  | 3 | S04 | PI-1 (Q1) | To Do
Task | T01.3.1.5 | US01.3.1 | E01 | F01.3 | Print a login summary table at the end of the seed |  | Platform | Platform |  |  | 2 | S04 | PI-1 (Q1) | To Do
Epic | E02 |  | E02 |  | Identity, Access & Security Baseline | Authentication, MFA, the RBAC model and the audit trail that compliance depends on. | Platform | Platform | Must | 44 | 112 |  | PI-1 (Q1) | To Do |  | Gates every write path in the system.
Feature | F02.1 | E02 | E02 | F02.1 | Authentication and staff MFA | Password + TOTP for staff; residents authenticate without MFA friction. | Platform | Platform | Must | 13 | 32 |  | PI-1 (Q1) | To Do
User Story | US02.1.1 | F02.1 | E02 | F02.1 | As a barangay official, I sign in with a password and a one-time code | GIVEN a staff account WHEN I sign in THEN a 6-digit TOTP is required and an invalid code is rejected. | Platform | Platform | Must | 8 | 19 | S03 | PI-1 (Q1) | To Do
Task | T02.1.1.1 | US02.1.1 | E02 | F02.1 | Implement scrypt password hashing and constant-time verify |  | Platform | Platform |  |  | 4 | S03 | PI-1 (Q1) | To Do
Task | T02.1.1.2 | US02.1.1 | E02 | F02.1 | Implement JWT issue/verify with scope claims |  | Platform | Platform |  |  | 4 | S03 | PI-1 (Q1) | To Do
Task | T02.1.1.3 | US02.1.1 | E02 | F02.1 | Implement RFC 6238 TOTP with a +/-1 step window |  | Platform | Platform |  |  | 5 | S03 | PI-1 (Q1) | To Do
Task | T02.1.1.4 | US02.1.1 | E02 | F02.1 | Build lazy MFA enrolment returning the otpauth URI |  | Platform | Platform |  |  | 4 | S03 | PI-1 (Q1) | To Do
Task | T02.1.1.5 | US02.1.1 | E02 | F02.1 | Return a uniform failure to prevent user enumeration |  | Platform | Platform |  |  | 2 | S03 | PI-1 (Q1) | To Do
User Story | US02.1.2 | F02.1 | E02 | F02.1 | As a resident, I sign in without MFA so the app stays usable on a cheap phone | GIVEN a resident account WHEN I sign in with email and password THEN I receive a session without a TOTP challenge. | Platform | Platform | Must | 2 | 5 | S03 | PI-1 (Q1) | To Do
Task | T02.1.2.1 | US02.1.2 | E02 | F02.1 | Branch MFA requirement on the isStaff role flag |  | Platform | Platform |  |  | 2 | S03 | PI-1 (Q1) | To Do
Task | T02.1.2.2 | US02.1.2 | E02 | F02.1 | Add session records with IP and user agent |  | Platform | Platform |  |  | 3 | S03 | PI-1 (Q1) | To Do
User Story | US02.1.3 | F02.1 | E02 | F02.1 | As an admin, I can reset a user's MFA when they lose their phone | GIVEN a locked-out user WHEN an admin resets MFA THEN the next login re-enrols and the action is audited. | Platform | Platform | Must | 3 | 8 | S05 | PI-1 (Q1) | To Do
Task | T02.1.3.1 | US02.1.3 | E02 | F02.1 | Add MFA reset endpoint with admin permission |  | Platform | Platform |  |  | 3 | S05 | PI-1 (Q1) | To Do
Task | T02.1.3.2 | US02.1.3 | E02 | F02.1 | Audit the reset with actor and target |  | Platform | Platform |  |  | 2 | S05 | PI-1 (Q1) | To Do
Task | T02.1.3.3 | US02.1.3 | E02 | F02.1 | Add the reset control to User Management |  | Platform | Platform |  |  | 3 | S05 | PI-1 (Q1) | To Do
Feature | F02.2 | E02 | E02 | F02.2 | Role-based access control | 14 roles across module:action permissions, enforced server-side. | Platform | Platform | Must | 18 | 44 |  | PI-1 (Q1) | To Do
User Story | US02.2.1 | F02.2 | E02 | F02.2 | As a security lead, permissions are declared once and enforced everywhere | GIVEN a role WHEN it calls any endpoint THEN access is decided by module:action permissions, never by the client. | Platform | Platform | Must | 8 | 21 | S04 | PI-1 (Q1) | To Do
Task | T02.2.1.1 | US02.2.1 | E02 | F02.2 | Define the module and action catalog |  | Platform | Platform |  |  | 4 | S04 | PI-1 (Q1) | To Do
Task | T02.2.1.2 | US02.2.1 | E02 | F02.2 | Map all 14 roles to permission sets |  | Platform | Platform |  |  | 6 | S04 | PI-1 (Q1) | To Do
Task | T02.2.1.3 | US02.2.1 | E02 | F02.2 | Implement can/assertCan guards and ForbiddenError |  | Platform | Platform |  |  | 3 | S04 | PI-1 (Q1) | To Do
Task | T02.2.1.4 | US02.2.1 | E02 | F02.2 | Seed roles and permissions into the database |  | Platform | Platform |  |  | 3 | S04 | PI-1 (Q1) | To Do
Task | T02.2.1.5 | US02.2.1 | E02 | F02.2 | Unit-test each role's capability boundaries |  | Platform | Platform |  |  | 5 | S04 | PI-1 (Q1) | To Do
User Story | US02.2.2 | F02.2 | E02 | F02.2 | As a VAW desk officer, only I and the Punong Barangay can read VAWC records | GIVEN a confidential VAWC record WHEN any other role lists blotter entries THEN the row is absent from the API response entirely. | Platform | Platform | Must | 5 | 14 | S05 | PI-1 (Q1) | To Do
Task | T02.2.2.1 | US02.2.2 | E02 | F02.2 | Add isConfidential flag and canSeeConfidentialCase guard |  | Platform | Platform |  |  | 3 | S05 | PI-1 (Q1) | To Do
Task | T02.2.2.2 | US02.2.2 | E02 | F02.2 | Filter confidential rows server-side in list and detail |  | Platform | Platform |  |  | 4 | S05 | PI-1 (Q1) | To Do
Task | T02.2.2.3 | US02.2.2 | E02 | F02.2 | Redact narratives in list views even for permitted roles |  | Platform | Platform |  |  | 2 | S05 | PI-1 (Q1) | To Do
Task | T02.2.2.4 | US02.2.2 | E02 | F02.2 | Audit every confidential record read |  | Platform | Platform |  |  | 2 | S05 | PI-1 (Q1) | To Do
Task | T02.2.2.5 | US02.2.2 | E02 | F02.2 | Test that the secretary receives zero confidential rows |  | Platform | Platform |  |  | 3 | S05 | PI-1 (Q1) | To Do
User Story | US02.2.3 | F02.2 | E02 | F02.2 | As a DILG viewer, I see aggregates but never raw personal data | GIVEN the DILG viewer role WHEN a raw PII query is attempted THEN it is refused, while aggregate endpoints succeed. | Platform | Platform | Must | 5 | 9 | S05 | PI-1 (Q1) | To Do
Task | T02.2.3.1 | US02.2.3 | E02 | F02.2 | Add aggregatesOnly to the tenant scope |  | Platform | Platform |  |  | 3 | S05 | PI-1 (Q1) | To Do
Task | T02.2.3.2 | US02.2.3 | E02 | F02.2 | Reject non-aggregate operations at the data layer |  | Platform | Platform |  |  | 4 | S05 | PI-1 (Q1) | To Do
Task | T02.2.3.3 | US02.2.3 | E02 | F02.2 | Verify quarterly rollups still resolve |  | Platform | Platform |  |  | 2 | S05 | PI-1 (Q1) | To Do
Feature | F02.3 | E02 | E02 | F02.3 | Audit trail and data-privacy controls | RA 10173 obligations: audit, consent, encryption and data-subject rights. | Platform | Platform | Must | 13 | 36 |  | PI-1 (Q1) | To Do
User Story | US02.3.1 | F02.3 | E02 | F02.3 | As a compliance officer, every privileged action is written to an immutable audit log | GIVEN any mutation WHEN it succeeds THEN an audit row records actor, role, tenant, entity, IP and timestamp. | Platform | Platform | Must | 5 | 16 | S04 | PI-1 (Q1) | To Do
Task | T02.3.1.1 | US02.3.1 | E02 | F02.3 | Add audit helper to the request context |  | Platform | Platform |  |  | 3 | S04 | PI-1 (Q1) | To Do
Task | T02.3.1.2 | US02.3.1 | E02 | F02.3 | Instrument all write endpoints |  | Platform | Platform |  |  | 6 | S04 | PI-1 (Q1) | To Do
Task | T02.3.1.3 | US02.3.1 | E02 | F02.3 | Flag AI-originated actions distinctly |  | Platform | Platform |  |  | 2 | S04 | PI-1 (Q1) | To Do
Task | T02.3.1.4 | US02.3.1 | E02 | F02.3 | Build the audit viewer screen |  | Platform | Platform |  |  | 5 | S04 | PI-1 (Q1) | To Do
User Story | US02.3.2 | F02.3 | E02 | F02.3 | As a data protection officer, sensitive columns are encrypted at rest | GIVEN KP narratives and health notes WHEN stored THEN they are AES-256-GCM encrypted and unreadable in the raw table. | Platform | Platform | Must | 5 | 12 | S06 | PI-1 (Q1) | To Do
Task | T02.3.2.1 | US02.3.2 | E02 | F02.3 | Implement encryptField/decryptField with versioned prefix |  | Platform | Platform |  |  | 5 | S06 | PI-1 (Q1) | To Do
Task | T02.3.2.2 | US02.3.2 | E02 | F02.3 | Apply to KP, blotter and health note columns |  | Platform | Platform |  |  | 4 | S06 | PI-1 (Q1) | To Do
Task | T02.3.2.3 | US02.3.2 | E02 | F02.3 | Document key rotation procedure |  | Platform | Platform |  |  | 3 | S06 | PI-1 (Q1) | To Do
User Story | US02.3.3 | F02.3 | E02 | F02.3 | As a resident, I can export everything the barangay holds about me | GIVEN a signed-in resident WHEN I request my data THEN a JSON export of my records downloads and the request is audited. | Platform | Platform | Must | 3 | 8 | S06 | PI-1 (Q1) | To Do
Task | T02.3.3.1 | US02.3.3 | E02 | F02.3 | Build the data-subject export endpoint |  | Platform | Platform |  |  | 4 | S06 | PI-1 (Q1) | To Do
Task | T02.3.3.2 | US02.3.3 | E02 | F02.3 | Add the download action to the resident app |  | Platform | Platform |  |  | 3 | S06 | PI-1 (Q1) | To Do
Task | T02.3.3.3 | US02.3.3 | E02 | F02.3 | Note that BIMS-held records remain under DILG custody |  | Platform | Platform |  |  | 1 | S06 | PI-1 (Q1) | To Do
Epic | E03 |  | E03 |  | Resident Registry — BIPS Parity | Households and inhabitants: the identity backbone every other module references. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 24 | 70 |  | PI-1 (Q1) | To Do |  | Encode once — every module reads from here.
Feature | F03.1 | E03 | E03 | F03.1 | Household and inhabitant records | Record of Barangay Inhabitants with PhilSys-ready profiles and sectoral flags. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 16 | 46 |  | PI-1 (Q1) | To Do
User Story | US03.1.1 | F03.1 | E03 | F03.1 | As a barangay secretary, I can register a household and its members | GIVEN a new household WHEN I save it THEN it receives a household number, an address with purok, and members linked to a head. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 8 | 27 | S05 | PI-1 (Q1) | To Do
Task | T03.1.1.1 | US03.1.1 | E03 | F03.1 | Build household create/edit API with Zod contracts |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 5 | S05 | PI-1 (Q1) | To Do
Task | T03.1.1.2 | US03.1.1 | E03 | F03.1 | Build inhabitant create/edit with sectoral flags |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 6 | S05 | PI-1 (Q1) | To Do
Task | T03.1.1.3 | US03.1.1 | E03 | F03.1 | Auto-derive senior status from birth date |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 2 | S05 | PI-1 (Q1) | To Do
Task | T03.1.1.4 | US03.1.1 | E03 | F03.1 | Build the household list and detail screens |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 8 | S05 | PI-1 (Q1) | To Do
Task | T03.1.1.5 | US03.1.1 | E03 | F03.1 | Build the inhabitant list with purok and sector filters |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 6 | S05 | PI-1 (Q1) | To Do
User Story | US03.1.2 | F03.1 | E03 | F03.1 | As a secretary, the system warns me before I create a duplicate resident | GIVEN a matching surname and birth date WHEN I save THEN a 409 lists candidate matches and I may override deliberately. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 5 | 13 | S06 | PI-1 (Q1) | To Do
Task | T03.1.2.1 | US03.1.2 | E03 | F03.1 | Implement surname + birthdate fuzzy dedupe check |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 5 | S06 | PI-1 (Q1) | To Do
Task | T03.1.2.2 | US03.1.2 | E03 | F03.1 | Return candidates with a 409 response |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 2 | S06 | PI-1 (Q1) | To Do
Task | T03.1.2.3 | US03.1.2 | E03 | F03.1 | Build the review-and-override UI |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 4 | S06 | PI-1 (Q1) | To Do
Task | T03.1.2.4 | US03.1.2 | E03 | F03.1 | Test the override path sets confirmDuplicate |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 2 | S06 | PI-1 (Q1) | To Do
User Story | US03.1.3 | F03.1 | E03 | F03.1 | As a secretary, I can see how complete a resident's profile is | GIVEN a resident record WHEN I open it THEN a completeness percentage shows which key fields are missing. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 3 | 6 | S06 | PI-1 (Q1) | To Do
Task | T03.1.3.1 | US03.1.3 | E03 | F03.1 | Compute completeness across key fields |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 3 | S06 | PI-1 (Q1) | To Do
Task | T03.1.3.2 | US03.1.3 | E03 | F03.1 | Render a progress meter on the detail screen |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 3 | S06 | PI-1 (Q1) | To Do
Feature | F03.2 | E03 | E03 | F03.2 | Consent registry (RA 10173) | Per-household consent artifacts that gate downstream use of personal data. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 5 | 16 |  | PI-1 (Q1) | To Do
User Story | US03.2.1 | F03.2 | E03 | F03.2 | As a DPO, no household data is used beyond operations without recorded consent | GIVEN a household WHEN consent is granted or withdrawn THEN the purpose, signatory, date and evidence are recorded and audited. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 5 | 16 | S06 | PI-1 (Q1) | To Do
Task | T03.2.1.1 | US03.2.1 | E03 | F03.2 | Model consent purposes and status lifecycle |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 3 | S06 | PI-1 (Q1) | To Do
Task | T03.2.1.2 | US03.2.1 | E03 | F03.2 | Build grant and withdraw endpoints |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 4 | S06 | PI-1 (Q1) | To Do
Task | T03.2.1.3 | US03.2.1 | E03 | F03.2 | Build the household consent panel |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 5 | S06 | PI-1 (Q1) | To Do
Task | T03.2.1.4 | US03.2.1 | E03 | F03.2 | Block ayuda batches lacking disbursement consent |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 4 | S06 | PI-1 (Q1) | To Do
Feature | F03.3 | E03 | E03 | F03.3 | RBI export and reporting | Hand-over format shaped like the LGUSS-BIMS Form B fields. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 3 | 8 |  | PI-1 (Q1) | To Do
User Story | US03.3.1 | F03.3 | E03 | F03.3 | As a secretary, I can export the RBI in the BIMS column format | GIVEN the registry WHEN I export THEN a CSV downloads in BIMS Form B column order and the export is audited. | BIMS-parity: BIPS | Squad A — Registry & Services | Must | 3 | 8 | S07 | PI-1 (Q1) | To Do
Task | T03.3.1.1 | US03.3.1 | E03 | F03.3 | Implement the RBI CSV endpoint in Form B order |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 4 | S07 | PI-1 (Q1) | To Do
Task | T03.3.1.2 | US03.3.1 | E03 | F03.3 | Add a client-side download with auth headers |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 3 | S07 | PI-1 (Q1) | To Do
Task | T03.3.1.3 | US03.3.1 | E03 | F03.3 | Audit every export |  | BIMS-parity: BIPS | Squad A — Registry & Services |  |  | 1 | S07 | PI-1 (Q1) | To Do
Epic | E04 |  | E04 |  | Service Issuance — BCIS Parity | Certificates and clearances end to end: request, pay, approve, issue, verify. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 34 | 89 |  | PI-2 (Q2) | To Do |  | The highest-volume resident transaction; RA 11032 clock applies.
Feature | F04.1 | E04 | E04 | F04.1 | Certificate catalog and fee schedule | Admin-definable certificate types with fees, validity and requirements. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 5 | 15 |  | PI-2 (Q2) | To Do
User Story | US04.1.1 | F04.1 | E04 | F04.1 | As an admin, I can define certificate types with fees and requirements | GIVEN a certificate type WHEN configured THEN its fee, validity, requirements and exemptions publish to residents and the public site. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 5 | 15 | S07 | PI-2 (Q2) | To Do
Task | T04.1.1.1 | US04.1.1 | E04 | F04.1 | Model certificate types with requirements and exemptions |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 4 | S07 | PI-2 (Q2) | To Do
Task | T04.1.1.2 | US04.1.1 | E04 | F04.1 | Seed the six standard PH barangay certificates |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S07 | PI-2 (Q2) | To Do
Task | T04.1.1.3 | US04.1.1 | E04 | F04.1 | Expose fees and requirements publicly (anti-fixer transparency) |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S07 | PI-2 (Q2) | To Do
Task | T04.1.1.4 | US04.1.1 | E04 | F04.1 | Build the type management screen |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 5 | S07 | PI-2 (Q2) | To Do
Feature | F04.2 | E04 | E04 | F04.2 | Request, payment and approval workflow | Staff- or resident-initiated request through to a signed release. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 18 | 49 |  | PI-2 (Q2) | To Do
User Story | US04.2.1 | F04.2 | E04 | F04.2 | As a resident, I can request a barangay clearance from my phone | GIVEN a signed-in resident WHEN I submit a request THEN it appears with a reference number and an awaiting-payment status. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 5 | 15 | S08 | PI-2 (Q2) | To Do
Task | T04.2.1.1 | US04.2.1 | E04 | F04.2 | Build the request endpoint with reference numbering |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 4 | S08 | PI-2 (Q2) | To Do
Task | T04.2.1.2 | US04.2.1 | E04 | F04.2 | Zero-fee types skip straight to approval |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 2 | S08 | PI-2 (Q2) | To Do
Task | T04.2.1.3 | US04.2.1 | E04 | F04.2 | Build the resident request flow UI |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 6 | S08 | PI-2 (Q2) | To Do
Task | T04.2.1.4 | US04.2.1 | E04 | F04.2 | Show fee and requirements before submission |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S08 | PI-2 (Q2) | To Do
User Story | US04.2.2 | F04.2 | E04 | F04.2 | As a resident, I can pay the fee from my wallet and get an official receipt | GIVEN an unpaid request WHEN I pay from my wallet THEN an OR number is issued, the ledger is credited and the status moves to for-approval — all atomically. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 8 | 20 | S09 | PI-2 (Q2) | To Do
Task | T04.2.2.1 | US04.2.2 | E04 | F04.2 | Implement pay-fee with EMI transfer |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 5 | S09 | PI-2 (Q2) | To Do
Task | T04.2.2.2 | US04.2.2 | E04 | F04.2 | Issue OR number and post the ledger credit in one transaction |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 5 | S09 | PI-2 (Q2) | To Do
Task | T04.2.2.3 | US04.2.2 | E04 | F04.2 | Handle insufficient balance with an OTC fallback message |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S09 | PI-2 (Q2) | To Do
Task | T04.2.2.4 | US04.2.2 | E04 | F04.2 | Waive exempt certificates (indigency, first-time jobseeker) |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 2 | S09 | PI-2 (Q2) | To Do
Task | T04.2.2.5 | US04.2.2 | E04 | F04.2 | Build the payment UI and status timeline |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 5 | S09 | PI-2 (Q2) | To Do
User Story | US04.2.3 | F04.2 | E04 | F04.2 | As a Punong Barangay, I approve or reject a request — a human always signs | GIVEN a paid request WHEN I approve it THEN it is released with an expiry and a verification code; rejection requires a reason. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 5 | 14 | S09 | PI-2 (Q2) | To Do
Task | T04.2.3.1 | US04.2.3 | E04 | F04.2 | Implement approve/reject with permission checks |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 4 | S09 | PI-2 (Q2) | To Do
Task | T04.2.3.2 | US04.2.3 | E04 | F04.2 | Generate the verification code and expiry |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S09 | PI-2 (Q2) | To Do
Task | T04.2.3.3 | US04.2.3 | E04 | F04.2 | Record processing time for RA 11032 metrics |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 2 | S09 | PI-2 (Q2) | To Do
Task | T04.2.3.4 | US04.2.3 | E04 | F04.2 | Build the approval queue screen |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 5 | S09 | PI-2 (Q2) | To Do
Feature | F04.3 | E04 | E04 | F04.3 | Document rendering and public verification | A QR-verifiable certificate anyone can check without logging in. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 11 | 25 |  | PI-2 (Q2) | To Do
User Story | US04.3.1 | F04.3 | E04 | F04.3 | As a resident, my released certificate renders as a printable document | GIVEN a released request WHEN I open it THEN the certificate body renders from the barangay template with the verification code. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 5 | 11 | S10 | PI-2 (Q2) | To Do
Task | T04.3.1.1 | US04.3.1 | E04 | F04.3 | Implement template rendering with placeholders |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 4 | S10 | PI-2 (Q2) | To Do
Task | T04.3.1.2 | US04.3.1 | E04 | F04.3 | Build the print-friendly document view |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 5 | S10 | PI-2 (Q2) | To Do
Task | T04.3.1.3 | US04.3.1 | E04 | F04.3 | Add the verify code and public link |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 2 | S10 | PI-2 (Q2) | To Do
User Story | US04.3.2 | F04.3 | E04 | F04.3 | As an employer, I can verify a certificate without an account | GIVEN a verification code WHEN opened publicly THEN validity, type, barangay and the holder's initials only are shown. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 3 | 9 | S10 | PI-2 (Q2) | To Do
Task | T04.3.2.1 | US04.3.2 | E04 | F04.3 | Build the public verify endpoint returning initials only |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S10 | PI-2 (Q2) | To Do
Task | T04.3.2.2 | US04.3.2 | E04 | F04.3 | Build the verify result page (valid/expired/not found) |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 4 | S10 | PI-2 (Q2) | To Do
Task | T04.3.2.3 | US04.3.2 | E04 | F04.3 | Confirm no full name or address is exposed |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 2 | S10 | PI-2 (Q2) | To Do
User Story | US04.3.3 | F04.3 | E04 | F04.3 | As a manager, I can see whether we meet the RA 11032 turnaround | GIVEN released requests WHEN I open the stats THEN median processing time and a compliance indicator are shown. | BIMS-parity: BCIS | Squad A — Registry & Services | Must | 3 | 5 | S10 | PI-2 (Q2) | To Do
Task | T04.3.3.1 | US04.3.3 | E04 | F04.3 | Compute median processing time over 30 days |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 3 | S10 | PI-2 (Q2) | To Do
Task | T04.3.3.2 | US04.3.3 | E04 | F04.3 | Add the compliance chip to the certificates screen |  | BIMS-parity: BCIS | Squad A — Registry & Services |  |  | 2 | S10 | PI-2 (Q2) | To Do
Epic | E05 |  | E05 |  | Financial Management — BFMS Parity | Budget, double-entry ledger and COA-aligned reporting. The books the wallet posts into. | BIMS-parity: BFMS | Squad B — Money | Must | 18 | 51 |  | PI-2 (Q2) | To Do |  | Reconciliation must be a by-product of transactions, not a monthly chore.
Feature | F05.1 | E05 | E05 | F05.1 | Annual budget and appropriations | COA expense classes, SK fund sub-ledger and utilisation tracking. | BIMS-parity: BFMS | Squad B — Money | Must | 5 | 16 |  | PI-2 (Q2) | To Do
User Story | US05.1.1 | F05.1 | E05 | F05.1 | As a treasurer, I can record the annual budget by COA expense class | GIVEN an appropriation ordinance WHEN recorded THEN budget lines exist by PS/MOOE/CO with obligated and disbursed tracking. | BIMS-parity: BFMS | Squad B — Money | Must | 5 | 16 | S08 | PI-2 (Q2) | To Do
Task | T05.1.1.1 | US05.1.1 | E05 | F05.1 | Model budget, budget lines and fund types |  | BIMS-parity: BFMS | Squad B — Money |  |  | 4 | S08 | PI-2 (Q2) | To Do
Task | T05.1.1.2 | US05.1.1 | E05 | F05.1 | Build budget CRUD endpoints |  | BIMS-parity: BFMS | Squad B — Money |  |  | 4 | S08 | PI-2 (Q2) | To Do
Task | T05.1.1.3 | US05.1.1 | E05 | F05.1 | Build the budget screen with utilisation bars |  | BIMS-parity: BFMS | Squad B — Money |  |  | 6 | S08 | PI-2 (Q2) | To Do
Task | T05.1.1.4 | US05.1.1 | E05 | F05.1 | Link the budget to its enacting ordinance |  | BIMS-parity: BFMS | Squad B — Money |  |  | 2 | S08 | PI-2 (Q2) | To Do
Feature | F05.2 | E05 | E05 | F05.2 | Double-entry ledger and receipts | Every peso movement posts a ledger entry with an OR or DV reference. | BIMS-parity: BFMS | Squad B — Money | Must | 13 | 35 |  | PI-2 (Q2) | To Do
User Story | US05.2.1 | F05.2 | E05 | F05.2 | As a treasurer, every collection and disbursement posts to the ledger automatically | GIVEN a wallet transaction WHEN it completes THEN a matching ledger entry is written in the same database transaction. | BIMS-parity: BFMS | Squad B — Money | Must | 8 | 22 | S09 | PI-2 (Q2) | To Do
Task | T05.2.1.1 | US05.2.1 | E05 | F05.2 | Model ledger entries with fund, account code and direction |  | BIMS-parity: BFMS | Squad B — Money |  |  | 4 | S09 | PI-2 (Q2) | To Do
Task | T05.2.1.2 | US05.2.1 | E05 | F05.2 | Post credits on fee collection with OR numbers |  | BIMS-parity: BFMS | Squad B — Money |  |  | 4 | S09 | PI-2 (Q2) | To Do
Task | T05.2.1.3 | US05.2.1 | E05 | F05.2 | Post debits on disbursement with DV numbers |  | BIMS-parity: BFMS | Squad B — Money |  |  | 4 | S09 | PI-2 (Q2) | To Do
Task | T05.2.1.4 | US05.2.1 | E05 | F05.2 | Build the ledger screen with fund and direction filters |  | BIMS-parity: BFMS | Squad B — Money |  |  | 6 | S09 | PI-2 (Q2) | To Do
Task | T05.2.1.5 | US05.2.1 | E05 | F05.2 | Build the official receipt register |  | BIMS-parity: BFMS | Squad B — Money |  |  | 4 | S09 | PI-2 (Q2) | To Do
User Story | US05.2.2 | F05.2 | E05 | F05.2 | As an auditor, I can produce a COA-aligned statement of receipts and expenditures | GIVEN a period WHEN I generate the SER THEN totals tie to the ledger to the peso and export cleanly. | BIMS-parity: BFMS | Squad B — Money | Must | 5 | 13 | S11 | PI-2 (Q2) | To Do
Task | T05.2.2.1 | US05.2.2 | E05 | F05.2 | Implement the SER aggregation query |  | BIMS-parity: BFMS | Squad B — Money |  |  | 5 | S11 | PI-2 (Q2) | To Do
Task | T05.2.2.2 | US05.2.2 | E05 | F05.2 | Build the report view and CSV export |  | BIMS-parity: BFMS | Squad B — Money |  |  | 5 | S11 | PI-2 (Q2) | To Do
Task | T05.2.2.3 | US05.2.2 | E05 | F05.2 | Reconcile against seeded wallet transactions |  | BIMS-parity: BFMS | Squad B — Money |  |  | 3 | S11 | PI-2 (Q2) | To Do
Epic | E06 |  | E06 |  | Barangay E-Wallet — Core Rails | The flagship differentiator: cashless disbursement and collection under BSP rules. | CBMS exclusive | Squad B — Money | Must | 44 | 116 |  | PI-2 (Q2) | To Do |  | CBMS never holds funds — a licensed EMI is the issuer of record.
Feature | F06.1 | E06 | E06 | F06.1 | Payments provider seam and wallets | A clean EmiProvider interface with a mock implementation for pilots. | CBMS exclusive | Squad B — Money | Must | 13 | 32 |  | PI-2 (Q2) | To Do
User Story | US06.1.1 | F06.1 | E06 | F06.1 | As an architect, a real EMI can be plugged in without touching product code | GIVEN the EmiProvider interface WHEN a provider is swapped THEN no module outside packages/payments changes. | CBMS exclusive | Squad B — Money | Must | 8 | 16 | S08 | PI-2 (Q2) | To Do
Task | T06.1.1.1 | US06.1.1 | E06 | F06.1 | Define the EmiProvider interface (transfer, batch, CICO, QR, billPay) |  | CBMS exclusive | Squad B — Money |  |  | 5 | S08 | PI-2 (Q2) | To Do
Task | T06.1.1.2 | US06.1.1 | E06 | F06.1 | Implement the mock provider with an in-memory settlement book |  | CBMS exclusive | Squad B — Money |  |  | 6 | S08 | PI-2 (Q2) | To Do
Task | T06.1.1.3 | US06.1.1 | E06 | F06.1 | Add webhook simulation hooks |  | CBMS exclusive | Squad B — Money |  |  | 3 | S08 | PI-2 (Q2) | To Do
Task | T06.1.1.4 | US06.1.1 | E06 | F06.1 | Label mock mode visibly in every UI |  | CBMS exclusive | Squad B — Money |  |  | 2 | S08 | PI-2 (Q2) | To Do
User Story | US06.1.2 | F06.1 | E06 | F06.1 | As a resident, I have a wallet with a KYC tier appropriate to my limits | GIVEN a resident WHEN a wallet is created THEN it starts at tier 1 with a low limit and can be upgraded to tier 2. | CBMS exclusive | Squad B — Money | Must | 5 | 16 | S09 | PI-2 (Q2) | To Do
Task | T06.1.2.1 | US06.1.2 | E06 | F06.1 | Model wallets, owner types and KYC tiers |  | CBMS exclusive | Squad B — Money |  |  | 4 | S09 | PI-2 (Q2) | To Do
Task | T06.1.2.2 | US06.1.2 | E06 | F06.1 | Implement wallet provisioning linked to inhabitants |  | CBMS exclusive | Squad B — Money |  |  | 4 | S09 | PI-2 (Q2) | To Do
Task | T06.1.2.3 | US06.1.2 | E06 | F06.1 | Build the wallet list and balance views |  | CBMS exclusive | Squad B — Money |  |  | 5 | S09 | PI-2 (Q2) | To Do
Task | T06.1.2.4 | US06.1.2 | E06 | F06.1 | Implement the KYC upgrade path |  | CBMS exclusive | Squad B — Money |  |  | 3 | S09 | PI-2 (Q2) | To Do
Feature | F06.2 | E06 | E06 | F06.2 | Government disbursement with maker–checker | Payroll, honoraria and ayuda paid in bulk, with segregation of duties. | CBMS exclusive | Squad B — Money | Must | 21 | 56 |  | PI-2 (Q2) | To Do
User Story | US06.2.1 | F06.2 | E06 | F06.2 | As a treasurer, I can prepare a disbursement batch of payees and amounts | GIVEN a list of payees WHEN I submit a batch THEN it is created for-approval with a batch number and total. | CBMS exclusive | Squad B — Money | Must | 8 | 21 | S10 | PI-2 (Q2) | To Do
Task | T06.2.1.1 | US06.2.1 | E06 | F06.2 | Model batches, items and statuses |  | CBMS exclusive | Squad B — Money |  |  | 4 | S10 | PI-2 (Q2) | To Do
Task | T06.2.1.2 | US06.2.1 | E06 | F06.2 | Implement batch creation with wallet resolution |  | CBMS exclusive | Squad B — Money |  |  | 5 | S10 | PI-2 (Q2) | To Do
Task | T06.2.1.3 | US06.2.1 | E06 | F06.2 | Require disbursement consent for ayuda batches |  | CBMS exclusive | Squad B — Money |  |  | 4 | S10 | PI-2 (Q2) | To Do
Task | T06.2.1.4 | US06.2.1 | E06 | F06.2 | Build the batch builder UI with a running total |  | CBMS exclusive | Squad B — Money |  |  | 8 | S10 | PI-2 (Q2) | To Do
User Story | US06.2.2 | F06.2 | E06 | F06.2 | As a Punong Barangay, I approve a batch the treasurer prepared — never my own | GIVEN a batch WHEN its preparer attempts approval THEN it is refused; a different approver executes it successfully. | CBMS exclusive | Squad B — Money | Must | 8 | 22 | S11 | PI-2 (Q2) | To Do
Task | T06.2.2.1 | US06.2.2 | E06 | F06.2 | Implement assertDifferentApprover maker–checker guard |  | CBMS exclusive | Squad B — Money |  |  | 3 | S11 | PI-2 (Q2) | To Do
Task | T06.2.2.2 | US06.2.2 | E06 | F06.2 | Execute the batch through the EMI provider |  | CBMS exclusive | Squad B — Money |  |  | 5 | S11 | PI-2 (Q2) | To Do
Task | T06.2.2.3 | US06.2.2 | E06 | F06.2 | Credit payee wallets and debit the treasury atomically |  | CBMS exclusive | Squad B — Money |  |  | 5 | S11 | PI-2 (Q2) | To Do
Task | T06.2.2.4 | US06.2.2 | E06 | F06.2 | Post the ledger debit with a DV number |  | CBMS exclusive | Squad B — Money |  |  | 3 | S11 | PI-2 (Q2) | To Do
Task | T06.2.2.5 | US06.2.2 | E06 | F06.2 | Disable the approve button with an explanation for the preparer |  | CBMS exclusive | Squad B — Money |  |  | 3 | S11 | PI-2 (Q2) | To Do
Task | T06.2.2.6 | US06.2.2 | E06 | F06.2 | Test the self-approval refusal end to end |  | CBMS exclusive | Squad B — Money |  |  | 3 | S11 | PI-2 (Q2) | To Do
User Story | US06.2.3 | F06.2 | E06 | F06.2 | As a beneficiary without a wallet, I am still paid over the counter | GIVEN a payee with no wallet WHEN the batch executes THEN the item is marked otc_fallback rather than failed. | CBMS exclusive | Squad B — Money | Must | 3 | 9 | S11 | PI-2 (Q2) | To Do
Task | T06.2.3.1 | US06.2.3 | E06 | F06.2 | Mark wallet-less items as OTC fallback |  | CBMS exclusive | Squad B — Money |  |  | 3 | S11 | PI-2 (Q2) | To Do
Task | T06.2.3.2 | US06.2.3 | E06 | F06.2 | Produce the OTC release list for the cashier |  | CBMS exclusive | Squad B — Money |  |  | 4 | S11 | PI-2 (Q2) | To Do
Task | T06.2.3.3 | US06.2.3 | E06 | F06.2 | Show the fallback count on the batch summary |  | CBMS exclusive | Squad B — Money |  |  | 2 | S11 | PI-2 (Q2) | To Do
User Story | US06.2.4 | F06.2 | E06 | F06.2 | As a beneficiary, no fee is ever deducted from my aid | GIVEN an ayuda disbursement WHEN executed THEN the beneficiary fee is zero by construction, not by configuration. | CBMS exclusive | Squad B — Money | Must | 2 | 4 | S11 | PI-2 (Q2) | To Do
Task | T06.2.4.1 | US06.2.4 | E06 | F06.2 | Force zero fee on disbursement items in code |  | CBMS exclusive | Squad B — Money |  |  | 2 | S11 | PI-2 (Q2) | To Do
Task | T06.2.4.2 | US06.2.4 | E06 | F06.2 | Unit-test that ayuda cannot carry a fee |  | CBMS exclusive | Squad B — Money |  |  | 2 | S11 | PI-2 (Q2) | To Do
Feature | F06.3 | E06 | E06 | F06.3 | Collections, bills and merchant payments | Money flowing back in: fees, biller collections and QR acceptance. | CBMS exclusive | Squad B — Money | Must | 10 | 28 |  | PI-2 (Q2) | To Do
User Story | US06.3.1 | F06.3 | E06 | F06.3 | As a resident, I can pay bills from my wallet | GIVEN a biller and account number WHEN I pay THEN the transaction records a transparent convenience fee shown up front. | CBMS exclusive | Squad B — Money | Must | 5 | 15 | S12 | PI-2 (Q2) | To Do
Task | T06.3.1.1 | US06.3.1 | E06 | F06.3 | Model billers and bill payments |  | CBMS exclusive | Squad B — Money |  |  | 3 | S12 | PI-2 (Q2) | To Do
Task | T06.3.1.2 | US06.3.1 | E06 | F06.3 | Implement billPay through the provider seam |  | CBMS exclusive | Squad B — Money |  |  | 4 | S12 | PI-2 (Q2) | To Do
Task | T06.3.1.3 | US06.3.1 | E06 | F06.3 | Build the biller directory and payment UI |  | CBMS exclusive | Squad B — Money |  |  | 6 | S12 | PI-2 (Q2) | To Do
Task | T06.3.1.4 | US06.3.1 | E06 | F06.3 | Display the convenience fee before confirmation |  | CBMS exclusive | Squad B — Money |  |  | 2 | S12 | PI-2 (Q2) | To Do
User Story | US06.3.2 | F06.3 | E06 | F06.3 | As a sari-sari owner, I can accept payment by QR | GIVEN a merchant QR WHEN a resident pays THEN funds move to the merchant wallet at the configured MDR (0% at launch). | CBMS exclusive | Squad B — Money | Must | 5 | 13 | S12 | PI-2 (Q2) | To Do
Task | T06.3.2.1 | US06.3.2 | E06 | F06.3 | Model merchants with QR codes and MDR in basis points |  | CBMS exclusive | Squad B — Money |  |  | 3 | S12 | PI-2 (Q2) | To Do
Task | T06.3.2.2 | US06.3.2 | E06 | F06.3 | Implement qrGenerate and qrPay |  | CBMS exclusive | Squad B — Money |  |  | 4 | S12 | PI-2 (Q2) | To Do
Task | T06.3.2.3 | US06.3.2 | E06 | F06.3 | Build merchant onboarding |  | CBMS exclusive | Squad B — Money |  |  | 5 | S12 | PI-2 (Q2) | To Do
Task | T06.3.2.4 | US06.3.2 | E06 | F06.3 | Default MDR to zero to build acceptance |  | CBMS exclusive | Squad B — Money |  |  | 1 | S12 | PI-2 (Q2) | To Do
Epic | E07 |  | E07 |  | Agent & Merchant Network (CICO) | Cash-in/cash-out through trusted local outlets — the trust anchor of the whole wallet. | CBMS exclusive | Squad B — Money | Must | 18 | 47 |  | PI-2 (Q2) | To Do |  | Liquidity failure on payout day is the single biggest adoption risk.
Feature | F07.1 | E07 | E07 | F07.1 | Agent app and cash-out flow | A mobile-first app for sari-sari stores, pawnshops and remittance outlets. | CBMS exclusive | Squad B — Money | Must | 13 | 33 |  | PI-2 (Q2) | To Do
User Story | US07.1.1 | F07.1 | E07 | F07.1 | As an agent, I can cash out a resident's aid with no fee | GIVEN a government-aid cash-out WHEN processed THEN the fee is zero and both the wallet and my cash-on-hand update. | CBMS exclusive | Squad B — Money | Must | 8 | 23 | S12 | PI-2 (Q2) | To Do
Task | T07.1.1.1 | US07.1.1 | E07 | F07.1 | Model agents, commissions and cash-on-hand |  | CBMS exclusive | Squad B — Money |  |  | 4 | S12 | PI-2 (Q2) | To Do
Task | T07.1.1.2 | US07.1.1 | E07 | F07.1 | Implement the cash-out endpoint with a zero government-aid fee |  | CBMS exclusive | Squad B — Money |  |  | 5 | S12 | PI-2 (Q2) | To Do
Task | T07.1.1.3 | US07.1.1 | E07 | F07.1 | Handle insufficient balance and agent-out-of-cash errors clearly |  | CBMS exclusive | Squad B — Money |  |  | 4 | S12 | PI-2 (Q2) | To Do
Task | T07.1.1.4 | US07.1.1 | E07 | F07.1 | Build the agent cash-out UI with a receipt |  | CBMS exclusive | Squad B — Money |  |  | 7 | S12 | PI-2 (Q2) | To Do
Task | T07.1.1.5 | US07.1.1 | E07 | F07.1 | Log the float movement |  | CBMS exclusive | Squad B — Money |  |  | 3 | S12 | PI-2 (Q2) | To Do
User Story | US07.1.2 | F07.1 | E07 | F07.1 | As an agent, I am warned before I run out of cash | GIVEN cash-on-hand below the threshold WHEN I open the app THEN a low-float warning explains how to request a rebalance. | CBMS exclusive | Squad B — Money | Must | 5 | 10 | S13 | PI-2 (Q2) | To Do
Task | T07.1.2.1 | US07.1.2 | E07 | F07.1 | Implement the float threshold and alert flag |  | CBMS exclusive | Squad B — Money |  |  | 3 | S13 | PI-2 (Q2) | To Do
Task | T07.1.2.2 | US07.1.2 | E07 | F07.1 | Build the float ledger screen |  | CBMS exclusive | Squad B — Money |  |  | 5 | S13 | PI-2 (Q2) | To Do
Task | T07.1.2.3 | US07.1.2 | E07 | F07.1 | Explain rebalancing ahead of disbursement day |  | CBMS exclusive | Squad B — Money |  |  | 2 | S13 | PI-2 (Q2) | To Do
Feature | F07.2 | E07 | E07 | F07.2 | Hub liquidity management | The LGU hub pre-funds and rebalances agents against the disbursement calendar. | CBMS exclusive | Squad B — Money | Must | 5 | 14 |  | PI-2 (Q2) | To Do
User Story | US07.2.1 | F07.2 | E07 | F07.2 | As an LGU operations lead, I can see which agents will run dry before payday | GIVEN an upcoming disbursement WHEN I open the liquidity view THEN agents below forecast demand are flagged for rebalancing. | CBMS exclusive | Squad B — Money | Must | 5 | 14 | S13 | PI-2 (Q2) | To Do
Task | T07.2.1.1 | US07.2.1 | E07 | F07.2 | Forecast cash demand from scheduled batches |  | CBMS exclusive | Squad B — Money |  |  | 5 | S13 | PI-2 (Q2) | To Do
Task | T07.2.1.2 | US07.2.1 | E07 | F07.2 | Build the agent liquidity dashboard |  | CBMS exclusive | Squad B — Money |  |  | 6 | S13 | PI-2 (Q2) | To Do
Task | T07.2.1.3 | US07.2.1 | E07 | F07.2 | Add rebalance recording |  | CBMS exclusive | Squad B — Money |  |  | 3 | S13 | PI-2 (Q2) | To Do
Epic | E08 |  | E08 |  | Justice & Safety — KPISBH Parity | Blotter, Katarungang Pambarangay case flow and the statutory clock under RA 7160. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 29 | 69 |  | PI-3 (Q3) | To Do |  | Statutory deadlines are computed, never typed.
Feature | F08.1 | E08 | E08 | F08.1 | Blotter and incident intake | The incident record book, with a hard-restricted VAWC track. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 10 | 24 |  | PI-3 (Q3) | To Do
User Story | US08.1.1 | F08.1 | E08 | F08.1 | As a tanod, I can record an incident in the blotter | GIVEN an incident WHEN recorded THEN it receives an entry number and the narrative is encrypted at rest. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 5 | 15 | S14 | PI-3 (Q3) | To Do
Task | T08.1.1.1 | US08.1.1 | E08 | F08.1 | Model blotter entries with categories |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 3 | S14 | PI-3 (Q3) | To Do
Task | T08.1.1.2 | US08.1.1 | E08 | F08.1 | Implement create with entry numbering |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 3 | S14 | PI-3 (Q3) | To Do
Task | T08.1.1.3 | US08.1.1 | E08 | F08.1 | Encrypt narratives at rest |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 3 | S14 | PI-3 (Q3) | To Do
Task | T08.1.1.4 | US08.1.1 | E08 | F08.1 | Build the blotter list and intake form |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 6 | S14 | PI-3 (Q3) | To Do
User Story | US08.1.2 | F08.1 | E08 | F08.1 | As a VAW desk officer, VAWC entries are invisible to other staff | GIVEN a VAWC entry WHEN another role lists the blotter THEN the row is absent and the category is unavailable to them. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 5 | 9 | S14 | PI-3 (Q3) | To Do
Task | T08.1.2.1 | US08.1.2 | E08 | F08.1 | Auto-flag VAWC entries confidential |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 2 | S14 | PI-3 (Q3) | To Do
Task | T08.1.2.2 | US08.1.2 | E08 | F08.1 | Restrict the category selector by permission |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 2 | S14 | PI-3 (Q3) | To Do
Task | T08.1.2.3 | US08.1.2 | E08 | F08.1 | Redact narratives in list views |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 2 | S14 | PI-3 (Q3) | To Do
Task | T08.1.2.4 | US08.1.2 | E08 | F08.1 | Test cross-role invisibility |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 3 | S14 | PI-3 (Q3) | To Do
Feature | F08.2 | E08 | E08 | F08.2 | KP case lifecycle and deadline engine | Mediation, conciliation, settlement, repudiation and CFA with computed timelines. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 19 | 45 |  | PI-3 (Q3) | To Do
User Story | US08.2.1 | F08.2 | E08 | F08.2 | As a Lupon secretary, the system computes the statutory deadlines for me | GIVEN a filed case WHEN opened THEN 15-day mediation, +15 conciliation and +15 extension deadlines are shown with days remaining. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 8 | 16 | S15 | PI-3 (Q3) | To Do
Task | T08.2.1.1 | US08.2.1 | E08 | F08.2 | Implement the RA 7160 s410 deadline engine |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 5 | S15 | PI-3 (Q3) | To Do
Task | T08.2.1.2 | US08.2.1 | E08 | F08.2 | Compute per-stage due dates and breach state |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 4 | S15 | PI-3 (Q3) | To Do
Task | T08.2.1.3 | US08.2.1 | E08 | F08.2 | Colour-code the countdown (green/gold/red) |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 3 | S15 | PI-3 (Q3) | To Do
Task | T08.2.1.4 | US08.2.1 | E08 | F08.2 | Unit-test each stage boundary |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 4 | S15 | PI-3 (Q3) | To Do
User Story | US08.2.2 | F08.2 | E08 | F08.2 | As a Punong Barangay, I can advance a case through its stages | GIVEN an open case WHEN I advance it THEN the stage updates, the case closes where applicable and the matching KP form is generated. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 8 | 22 | S15 | PI-3 (Q3) | To Do
Task | T08.2.2.1 | US08.2.2 | E08 | F08.2 | Implement the stage transition endpoint |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 4 | S15 | PI-3 (Q3) | To Do
Task | T08.2.2.2 | US08.2.2 | E08 | F08.2 | Auto-generate summons, notice, settlement and CFA documents |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 6 | S15 | PI-3 (Q3) | To Do
Task | T08.2.2.3 | US08.2.2 | E08 | F08.2 | Build the case detail with a hearing timeline |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 8 | S15 | PI-3 (Q3) | To Do
Task | T08.2.2.4 | US08.2.2 | E08 | F08.2 | Record parties and Pangkat members |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 4 | S15 | PI-3 (Q3) | To Do
User Story | US08.2.3 | F08.2 | E08 | F08.2 | As a Lupon secretary, I see which cases are about to breach their deadline | GIVEN open cases WHEN I open the deadline view THEN cases within five days are listed, breached ones first. | BIMS-parity: KPISBH | Squad A — Registry & Services | Must | 3 | 7 | S16 | PI-3 (Q3) | To Do
Task | T08.2.3.1 | US08.2.3 | E08 | F08.2 | Implement the deadline watch endpoint |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 3 | S16 | PI-3 (Q3) | To Do
Task | T08.2.3.2 | US08.2.3 | E08 | F08.2 | Surface at-risk cases on the dashboard |  | BIMS-parity: KPISBH | Squad A — Registry & Services |  |  | 4 | S16 | PI-3 (Q3) | To Do
Epic | E09 |  | E09 |  | Assets & Disaster Resilience — BAMS / BDRIS Parity | Property register, supplies inventory, hazard mapping and live disaster response. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 24 | 69 |  | PI-3 (Q3) | To Do |  | Property screens must mirror the BIMS console layout for familiarity.
Feature | F09.1 | E09 | E09 | F09.1 | Property and materials register | Infrastructure and non-infrastructure assets with custodianship under LGC s375. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 8 | 24 |  | PI-3 (Q3) | To Do
User Story | US09.1.1 | F09.1 | E09 | F09.1 | As a secretary, I can maintain the barangay property register | GIVEN the register WHEN opened THEN totals by type and status show, with filter, search and CSV export. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 5 | 18 | S16 | PI-3 (Q3) | To Do
Task | T09.1.1.1 | US09.1.1 | E09 | F09.1 | Model properties, status and governance category |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 3 | S16 | PI-3 (Q3) | To Do
Task | T09.1.1.2 | US09.1.1 | E09 | F09.1 | Build CRUD endpoints with filters |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 4 | S16 | PI-3 (Q3) | To Do
Task | T09.1.1.3 | US09.1.1 | E09 | F09.1 | Build the register screen mirroring the BIMS layout |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 8 | S16 | PI-3 (Q3) | To Do
Task | T09.1.1.4 | US09.1.1 | E09 | F09.1 | Add client-side CSV export |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 3 | S16 | PI-3 (Q3) | To Do
User Story | US09.1.2 | F09.1 | E09 | F09.1 | As a storekeeper, I can track supplies and see what needs reordering | GIVEN materials WHEN quantity falls to the reorder level THEN the item is flagged for reorder. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 3 | 6 | S16 | PI-3 (Q3) | To Do
Task | T09.1.2.1 | US09.1.2 | E09 | F09.1 | Model materials with reorder levels |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 2 | S16 | PI-3 (Q3) | To Do
Task | T09.1.2.2 | US09.1.2 | E09 | F09.1 | Build the inventory panel with reorder flags |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 4 | S16 | PI-3 (Q3) | To Do
Feature | F09.2 | E09 | E09 | F09.2 | Disaster preparedness and event response | Hazards per purok, evacuation centers, and an event mode that runs a real response. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 16 | 45 |  | PI-3 (Q3) | To Do
User Story | US09.2.1 | F09.2 | E09 | F09.2 | As a BDRRMC officer, I can map hazards and maintain evacuation centers | GIVEN puroks WHEN hazards are recorded THEN risk levels display, and evacuation centers show capacity and open state. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 5 | 13 | S17 | PI-3 (Q3) | To Do
Task | T09.2.1.1 | US09.2.1 | E09 | F09.2 | Model hazards and evacuation centers linked to assets |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 4 | S17 | PI-3 (Q3) | To Do
Task | T09.2.1.2 | US09.2.1 | E09 | F09.2 | Build hazard and center management screens |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 7 | S17 | PI-3 (Q3) | To Do
Task | T09.2.1.3 | US09.2.1 | E09 | F09.2 | Add open/close toggling for centers |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 2 | S17 | PI-3 (Q3) | To Do
User Story | US09.2.2 | F09.2 | E09 | F09.2 | As a BDRRMC officer, I can declare an event and track evacuation and relief | GIVEN a declared event WHEN households check in and relief is released THEN both are logged and deduplicated against the registry. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 8 | 25 | S17 | PI-3 (Q3) | To Do
Task | T09.2.2.1 | US09.2.2 | E09 | F09.2 | Implement event declaration and status flow |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 4 | S17 | PI-3 (Q3) | To Do
Task | T09.2.2.2 | US09.2.2 | E09 | F09.2 | Implement evacuation check-in/out per household |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 5 | S17 | PI-3 (Q3) | To Do
Task | T09.2.2.3 | US09.2.2 | E09 | F09.2 | Implement relief distribution with dedupe |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 5 | S17 | PI-3 (Q3) | To Do
Task | T09.2.2.4 | US09.2.2 | E09 | F09.2 | Build the event dashboard |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 7 | S17 | PI-3 (Q3) | To Do
Task | T09.2.2.5 | US09.2.2 | E09 | F09.2 | Feed the beneficiary list into an ayuda batch |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 4 | S17 | PI-3 (Q3) | To Do
User Story | US09.2.3 | F09.2 | E09 | F09.2 | As a responder, I know which residents are most vulnerable | GIVEN sectoral flags WHEN an event is active THEN bedridden, PWD and lone seniors are listed for priority assistance. | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | Should | 3 | 7 | S18 | PI-3 (Q3) | To Do
Task | T09.2.3.1 | US09.2.3 | E09 | F09.2 | Derive the vulnerable registry from sectoral flags |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 3 | S18 | PI-3 (Q3) | To Do
Task | T09.2.3.2 | US09.2.3 | E09 | F09.2 | Build the priority-assistance view |  | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services |  |  | 4 | S18 | PI-3 (Q3) | To Do
Epic | E10 |  | E10 |  | Resident Self-Service Suite | The resident-facing app: the entire surface LGUSS-BIMS has no equivalent for. | CBMS exclusive | Squad C — Resident & AI | Must | 49 | 153 |  | PI-3 (Q3) | To Do |  | Filipino/Taglish first; must work on a low-end Android phone.
Feature | F10.1 | E10 | E10 | F10.1 | Resident app shell, localisation and offline | An installable PWA that keeps working on a poor connection. | CBMS exclusive | Squad C — Resident & AI | Must | 13 | 36 |  | PI-3 (Q3) | To Do
User Story | US10.1.1 | F10.1 | E10 | F10.1 | As a resident, the app speaks Filipino by default | GIVEN the resident app WHEN opened THEN all strings render in Filipino/Taglish, with an English toggle that persists. | CBMS exclusive | Squad C — Resident & AI | Must | 5 | 15 | S14 | PI-3 (Q3) | To Do
Task | T10.1.1.1 | US10.1.1 | E10 | F10.1 | Build the i18n dictionary and useT hook |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S14 | PI-3 (Q3) | To Do
Task | T10.1.1.2 | US10.1.1 | E10 | F10.1 | Translate all resident-facing strings |  | CBMS exclusive | Squad C — Resident & AI |  |  | 8 | S14 | PI-3 (Q3) | To Do
Task | T10.1.1.3 | US10.1.1 | E10 | F10.1 | Add the language toggle with persistence |  | CBMS exclusive | Squad C — Resident & AI |  |  | 2 | S14 | PI-3 (Q3) | To Do
User Story | US10.1.2 | F10.1 | E10 | F10.1 | As a resident on a weak signal, the app still works | GIVEN intermittent connectivity WHEN I submit THEN the write queues locally and syncs, with sync state visible. | CBMS exclusive | Squad C — Resident & AI | Must | 8 | 21 | S18 | PI-3 (Q3) | To Do
Task | T10.1.2.1 | US10.1.2 | E10 | F10.1 | Add a service worker and app manifest |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S18 | PI-3 (Q3) | To Do
Task | T10.1.2.2 | US10.1.2 | E10 | F10.1 | Implement an IndexedDB write outbox |  | CBMS exclusive | Squad C — Resident & AI |  |  | 8 | S18 | PI-3 (Q3) | To Do
Task | T10.1.2.3 | US10.1.2 | E10 | F10.1 | Implement sync with server-wins conflict handling |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S18 | PI-3 (Q3) | To Do
Task | T10.1.2.4 | US10.1.2 | E10 | F10.1 | Show an explicit sync indicator |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S18 | PI-3 (Q3) | To Do
Feature | F10.2 | E10 | E10 | F10.2 | Report a Concern (311) and SOS | Being heard, and being safe — the two highest-impact resident features. | CBMS exclusive | Squad C — Resident & AI | Must | 13 | 44 |  | PI-3 (Q3) | To Do
User Story | US10.2.1 | F10.2 | E10 | F10.2 | As a resident, I can report a problem with a photo and my location | GIVEN a concern WHEN submitted THEN it receives a reference number and a 3-working-day SLA under RA 11032. | CBMS exclusive | Squad C — Resident & AI | Must | 5 | 23 | S15 | PI-3 (Q3) | To Do
Task | T10.2.1.1 | US10.2.1 | E10 | F10.2 | Model concerns with SLA due dates |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S15 | PI-3 (Q3) | To Do
Task | T10.2.1.2 | US10.2.1 | E10 | F10.2 | Implement create with geolocation capture |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S15 | PI-3 (Q3) | To Do
Task | T10.2.1.3 | US10.2.1 | E10 | F10.2 | Build the resident reporting UI |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S15 | PI-3 (Q3) | To Do
Task | T10.2.1.4 | US10.2.1 | E10 | F10.2 | Build the staff queue with SLA countdown |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S15 | PI-3 (Q3) | To Do
Task | T10.2.1.5 | US10.2.1 | E10 | F10.2 | Implement acknowledge/in-progress/resolve transitions |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S15 | PI-3 (Q3) | To Do
User Story | US10.2.2 | F10.2 | E10 | F10.2 | As a resident in danger, I can raise an alert with one tap | GIVEN an emergency WHEN I press SOS THEN responders see it live with my location, and a test mode exists for drills. | CBMS exclusive | Squad C — Resident & AI | Must | 8 | 21 | S16 | PI-3 (Q3) | To Do
Task | T10.2.2.1 | US10.2.2 | E10 | F10.2 | Model SOS alerts with kinds and test flag |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S16 | PI-3 (Q3) | To Do
Task | T10.2.2.2 | US10.2.2 | E10 | F10.2 | Implement raise and respond endpoints |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S16 | PI-3 (Q3) | To Do
Task | T10.2.2.3 | US10.2.2 | E10 | F10.2 | Build the one-tap SOS screen |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S16 | PI-3 (Q3) | To Do
Task | T10.2.2.4 | US10.2.2 | E10 | F10.2 | Build the auto-refreshing dispatch board |  | CBMS exclusive | Squad C — Resident & AI |  |  | 7 | S16 | PI-3 (Q3) | To Do
Task | T10.2.2.5 | US10.2.2 | E10 | F10.2 | Sort real emergencies ahead of tests |  | CBMS exclusive | Squad C — Resident & AI |  |  | 2 | S16 | PI-3 (Q3) | To Do
Feature | F10.3 | E10 | E10 | F10.3 | Appointments, feedback and identity | Skipping the queue, measuring satisfaction, and a verifiable digital ID. | CBMS exclusive | Squad C — Resident & AI | Must | 13 | 42 |  | PI-3 (Q3) | To Do
User Story | US10.3.1 | F10.3 | E10 | F10.3 | As a resident, I can book a slot instead of queueing at the hall | GIVEN available slots WHEN I book THEN I receive a queue number and the hall sees me on the day's list. | CBMS exclusive | Squad C — Resident & AI | Must | 5 | 18 | S18 | PI-3 (Q3) | To Do
Task | T10.3.1.1 | US10.3.1 | E10 | F10.3 | Model appointments and queue numbers |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S18 | PI-3 (Q3) | To Do
Task | T10.3.1.2 | US10.3.1 | E10 | F10.3 | Implement booking and status transitions |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S18 | PI-3 (Q3) | To Do
Task | T10.3.1.3 | US10.3.1 | E10 | F10.3 | Build resident booking and staff queue screens |  | CBMS exclusive | Squad C — Resident & AI |  |  | 7 | S18 | PI-3 (Q3) | To Do
Task | T10.3.1.4 | US10.3.1 | E10 | F10.3 | Add a kiosk now-serving display |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S18 | PI-3 (Q3) | To Do
User Story | US10.3.2 | F10.3 | E10 | F10.3 | As a resident, I can rate the service I received | GIVEN a completed transaction WHEN I rate it THEN the score feeds the CSM report and low scores raise a grievance. | CBMS exclusive | Squad C — Resident & AI | Must | 3 | 12 | S19 | PI-3 (Q3) | To Do
Task | T10.3.2.1 | US10.3.2 | E10 | F10.3 | Implement feedback capture with grievance flagging |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S19 | PI-3 (Q3) | To Do
Task | T10.3.2.2 | US10.3.2 | E10 | F10.3 | Build the one-tap rating UI |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S19 | PI-3 (Q3) | To Do
Task | T10.3.2.3 | US10.3.2 | E10 | F10.3 | Build the CSM summary with distribution |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S19 | PI-3 (Q3) | To Do
User Story | US10.3.3 | F10.3 | E10 | F10.3 | As a resident, I carry a verifiable digital barangay ID | GIVEN a verified resident WHEN I open my ID THEN a QR-backed card displays and staff scanning it see only permitted fields. | CBMS exclusive | Squad C — Resident & AI | Must | 5 | 12 | S19 | PI-3 (Q3) | To Do
Task | T10.3.3.1 | US10.3.3 | E10 | F10.3 | Model digital IDs with QR codes and expiry |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S19 | PI-3 (Q3) | To Do
Task | T10.3.3.2 | US10.3.3 | E10 | F10.3 | Build the ID card view |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S19 | PI-3 (Q3) | To Do
Task | T10.3.3.3 | US10.3.3 | E10 | F10.3 | Implement staff-side scan lookup with RBAC |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S19 | PI-3 (Q3) | To Do
Feature | F10.4 | E10 | E10 | F10.4 | Participation and transparency | Participatory budgeting, the digital assembly and two-way announcements. | CBMS exclusive | Squad C — Resident & AI | Must | 10 | 31 |  | PI-3 (Q3) | To Do
User Story | US10.4.1 | F10.4 | E10 | F10.4 | As a resident, I can vote on which project the barangay funds next | GIVEN an open cycle WHEN I vote THEN exactly one vote per resident is recorded and results publish to the transparency board. | CBMS exclusive | Squad C — Resident & AI | Must | 5 | 15 | S19 | PI-3 (Q3) | To Do
Task | T10.4.1.1 | US10.4.1 | E10 | F10.4 | Model cycles, options and votes with a uniqueness constraint |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S19 | PI-3 (Q3) | To Do
Task | T10.4.1.2 | US10.4.1 | E10 | F10.4 | Enforce one vote per verified resident |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S19 | PI-3 (Q3) | To Do
Task | T10.4.1.3 | US10.4.1 | E10 | F10.4 | Build the voting UI and results view |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S19 | PI-3 (Q3) | To Do
Task | T10.4.1.4 | US10.4.1 | E10 | F10.4 | Handle the already-voted case gracefully |  | CBMS exclusive | Squad C — Resident & AI |  |  | 2 | S19 | PI-3 (Q3) | To Do
User Story | US10.4.2 | F10.4 | E10 | F10.4 | As a resident, I receive barangay announcements and can reply | GIVEN a published announcement WHEN I open the app THEN it appears by severity and I can reply into a moderated inbox. | CBMS exclusive | Squad C — Resident & AI | Must | 5 | 16 | S20 | PI-3 (Q3) | To Do
Task | T10.4.2.1 | US10.4.2 | E10 | F10.4 | Model announcements, channels and replies |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S20 | PI-3 (Q3) | To Do
Task | T10.4.2.2 | US10.4.2 | E10 | F10.4 | Implement publish with channel selection |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S20 | PI-3 (Q3) | To Do
Task | T10.4.2.3 | US10.4.2 | E10 | F10.4 | Build the composer with an SMS cost warning |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S20 | PI-3 (Q3) | To Do
Task | T10.4.2.4 | US10.4.2 | E10 | F10.4 | Build the resident feed and reply flow |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S20 | PI-3 (Q3) | To Do
Epic | E11 |  | E11 |  | Health, Social Services & Livelihood | Turning the health module outward to residents, and connecting people to economic help. | Mixed — new capability | Squad C — Resident & AI | Should | 20 | 58 |  | PI-3 (Q3) | To Do |  | BIMS has no dedicated health module; largely new capability.
Feature | F11.1 | E11 | E11 | F11.1 | Health campaigns and records | BHW-managed cohorts drawn from the registry's sectoral flags. | Mixed — new capability | Squad C — Resident & AI | Should | 10 | 30 |  | PI-3 (Q3) | To Do
User Story | US11.1.1 | F11.1 | E11 | F11.1 | As a BHW, I can run a health campaign against a cohort | GIVEN a cohort filter WHEN a campaign runs THEN matching residents are listed and visits are recorded with encrypted notes. | Mixed — new capability | Squad C — Resident & AI | Should | 5 | 17 | S18 | PI-3 (Q3) | To Do
Task | T11.1.1.1 | US11.1.1 | E11 | F11.1 | Model campaigns with cohort filters |  | Mixed — new capability | Squad C — Resident & AI |  |  | 4 | S18 | PI-3 (Q3) | To Do
Task | T11.1.1.2 | US11.1.1 | E11 | F11.1 | Derive cohorts from sectoral flags |  | Mixed — new capability | Squad C — Resident & AI |  |  | 4 | S18 | PI-3 (Q3) | To Do
Task | T11.1.1.3 | US11.1.1 | E11 | F11.1 | Build campaign management and record capture |  | Mixed — new capability | Squad C — Resident & AI |  |  | 7 | S18 | PI-3 (Q3) | To Do
Task | T11.1.1.4 | US11.1.1 | E11 | F11.1 | Encrypt health notes at rest |  | Mixed — new capability | Squad C — Resident & AI |  |  | 2 | S18 | PI-3 (Q3) | To Do
User Story | US11.1.2 | F11.1 | E11 | F11.1 | As a resident, I can book a health-center visit and get reminders | GIVEN an active campaign WHEN I am in the cohort THEN I can book a slot and receive reminders in-app. | Mixed — new capability | Squad C — Resident & AI | Should | 5 | 13 | S19 | PI-3 (Q3) | To Do
Task | T11.1.2.1 | US11.1.2 | E11 | F11.1 | Link health bookings to the appointments module |  | Mixed — new capability | Squad C — Resident & AI |  |  | 4 | S19 | PI-3 (Q3) | To Do
Task | T11.1.2.2 | US11.1.2 | E11 | F11.1 | Build the resident health screen |  | Mixed — new capability | Squad C — Resident & AI |  |  | 5 | S19 | PI-3 (Q3) | To Do
Task | T11.1.2.3 | US11.1.2 | E11 | F11.1 | Implement reminder scheduling |  | Mixed — new capability | Squad C — Resident & AI |  |  | 4 | S19 | PI-3 (Q3) | To Do
Feature | F11.2 | E11 | E11 | F11.2 | Livelihood, jobs and benefit applications | A local job board and online applications for social programs. | Mixed — new capability | Squad C — Resident & AI | Should | 10 | 28 |  | PI-3 (Q3) | To Do
User Story | US11.2.1 | F11.2 | E11 | F11.2 | As a resident, I can find local jobs and training and apply online | GIVEN active postings WHEN I apply THEN my application is tracked and visible to the livelihood desk. | Mixed — new capability | Squad C — Resident & AI | Should | 5 | 14 | S20 | PI-3 (Q3) | To Do
Task | T11.2.1.1 | US11.2.1 | E11 | F11.2 | Model job posts and applications |  | Mixed — new capability | Squad C — Resident & AI |  |  | 3 | S20 | PI-3 (Q3) | To Do
Task | T11.2.1.2 | US11.2.1 | E11 | F11.2 | Build the job board and application flow |  | Mixed — new capability | Squad C — Resident & AI |  |  | 6 | S20 | PI-3 (Q3) | To Do
Task | T11.2.1.3 | US11.2.1 | E11 | F11.2 | Build the staff review queue |  | Mixed — new capability | Squad C — Resident & AI |  |  | 5 | S20 | PI-3 (Q3) | To Do
User Story | US11.2.2 | F11.2 | E11 | F11.2 | As a resident, I can apply for 4Ps, solo-parent, senior or PWD benefits | GIVEN a program WHEN I apply THEN the application routes to staff with a status I can follow. | Mixed — new capability | Squad C — Resident & AI | Should | 5 | 14 | S20 | PI-3 (Q3) | To Do
Task | T11.2.2.1 | US11.2.2 | E11 | F11.2 | Model benefit applications and statuses |  | Mixed — new capability | Squad C — Resident & AI |  |  | 3 | S20 | PI-3 (Q3) | To Do
Task | T11.2.2.2 | US11.2.2 | E11 | F11.2 | Build the application form and tracker |  | Mixed — new capability | Squad C — Resident & AI |  |  | 6 | S20 | PI-3 (Q3) | To Do
Task | T11.2.2.3 | US11.2.2 | E11 | F11.2 | Build the staff endorsement workflow |  | Mixed — new capability | Squad C — Resident & AI |  |  | 5 | S20 | PI-3 (Q3) | To Do
Epic | E12 |  | E12 |  | Governance & Legislative — BORIS / BDP / BBI / BGADPBMS | Ordinances, the development plan, barangay-based institutions and the GAD budget. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 18 | 55 |  | PI-4 (Q4) | To Do |  | Feeds the public transparency board.
Feature | F12.1 | E12 | E12 | F12.1 | Ordinances and resolutions registry | The legislative record, published automatically to the public site. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 5 | 16 |  | PI-4 (Q4) | To Do
User Story | US12.1.1 | F12.1 | E12 | F12.1 | As a Sangguniang Barangay member, I can register and publish legislation | GIVEN an enacted ordinance WHEN published THEN it appears on the public website with number, series and date. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 5 | 16 | S20 | PI-4 (Q4) | To Do
Task | T12.1.1.1 | US12.1.1 | E12 | F12.1 | Model legislation kinds, statuses and relations |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 4 | S20 | PI-4 (Q4) | To Do
Task | T12.1.1.2 | US12.1.1 | E12 | F12.1 | Build the registry screen with filters |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 6 | S20 | PI-4 (Q4) | To Do
Task | T12.1.1.3 | US12.1.1 | E12 | F12.1 | Implement the publish toggle |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 2 | S20 | PI-4 (Q4) | To Do
Task | T12.1.1.4 | US12.1.1 | E12 | F12.1 | Render the public legislation list |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 4 | S20 | PI-4 (Q4) | To Do
Feature | F12.2 | E12 | E12 | F12.2 | Development plan and projects | Multi-year plan with per-project status feeding participatory budgeting. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 5 | 14 |  | PI-4 (Q4) | To Do
User Story | US12.2.1 | F12.2 | E12 | F12.2 | As a planner, I can track development projects and their progress | GIVEN a plan WHEN projects are updated THEN budget, funding source, status and progress are visible publicly. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 5 | 14 | S21 | PI-4 (Q4) | To Do
Task | T12.2.1.1 | US12.2.1 | E12 | F12.2 | Model plans and projects with sectors |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 4 | S21 | PI-4 (Q4) | To Do
Task | T12.2.1.2 | US12.2.1 | E12 | F12.2 | Build the project tracker with progress editing |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 7 | S21 | PI-4 (Q4) | To Do
Task | T12.2.1.3 | US12.2.1 | E12 | F12.2 | Feed proposed projects into PB options |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 3 | S21 | PI-4 (Q4) | To Do
Feature | F12.3 | E12 | E12 | F12.3 | GAD plan and budget monitoring | The 5% GAD budget floor, checked rather than asserted. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 5 | 13 |  | PI-4 (Q4) | To Do
User Story | US12.3.1 | F12.3 | E12 | F12.3 | As a GAD focal person, the system checks the 5% budget floor for me | GIVEN a GAD plan WHEN the GAD budget is below 5% of the total THEN a clear non-compliance warning shows. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 5 | 13 | S21 | PI-4 (Q4) | To Do
Task | T12.3.1.1 | US12.3.1 | E12 | F12.3 | Model GAD plans and activities |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 3 | S21 | PI-4 (Q4) | To Do
Task | T12.3.1.2 | US12.3.1 | E12 | F12.3 | Compute the GAD share and compliance state |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 3 | S21 | PI-4 (Q4) | To Do
Task | T12.3.1.3 | US12.3.1 | E12 | F12.3 | Build the plan screen with the compliance chip |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 5 | S21 | PI-4 (Q4) | To Do
Task | T12.3.1.4 | US12.3.1 | E12 | F12.3 | Warn live while entering a non-compliant budget |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 2 | S21 | PI-4 (Q4) | To Do
Feature | F12.4 | E12 | E12 | F12.4 | Barangay-based institutions | The bodies that staff other modules: Lupon, BDRRMC, BADAC, BCPC, SK. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 3 | 12 |  | PI-4 (Q4) | To Do
User Story | US12.4.1 | F12.4 | E12 | F12.4 | As a secretary, I maintain the roster of barangay institutions | GIVEN an institution WHEN members are recorded THEN they link to resident records and feed the modules that use them. | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | Should | 3 | 12 | S21 | PI-4 (Q4) | To Do
Task | T12.4.1.1 | US12.4.1 | E12 | F12.4 | Model institutions, members and minutes |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 3 | S21 | PI-4 (Q4) | To Do
Task | T12.4.1.2 | US12.4.1 | E12 | F12.4 | Build the institution directory |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 6 | S21 | PI-4 (Q4) | To Do
Task | T12.4.1.3 | US12.4.1 | E12 | F12.4 | Link Lupon membership to KP and BDRRMC to disaster |  | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services |  |  | 3 | S21 | PI-4 (Q4) | To Do
Epic | E13 |  | E13 |  | AI Agentic Layer | A resident assistant, staff copilots and inspectable agentic workflows — with a human gate. | CBMS exclusive | Squad C — Resident & AI | Should | 39 | 108 |  | PI-4 (Q4) | To Do |  | AI drafts and recommends; a named official always signs.
Feature | F13.1 | E13 | E13 | F13.1 | AI platform, guardrails and cost control | Provider-agnostic orchestration with citations, audit and model routing. | CBMS exclusive | Squad C — Resident & AI | Should | 10 | 29 |  | PI-4 (Q4) | To Do
User Story | US13.1.1 | F13.1 | E13 | F13.1 | As an architect, AI providers are swappable and routed by cost | GIVEN a request WHEN it is high-volume THEN a fast model handles it, while hard tasks route to a capable model. | CBMS exclusive | Squad C — Resident & AI | Should | 5 | 15 | S21 | PI-4 (Q4) | To Do
Task | T13.1.1.1 | US13.1.1 | E13 | F13.1 | Define the AiProvider interface |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S21 | PI-4 (Q4) | To Do
Task | T13.1.1.2 | US13.1.1 | E13 | F13.1 | Implement the mock and Anthropic providers |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S21 | PI-4 (Q4) | To Do
Task | T13.1.1.3 | US13.1.1 | E13 | F13.1 | Implement tiered model routing |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S21 | PI-4 (Q4) | To Do
Task | T13.1.1.4 | US13.1.1 | E13 | F13.1 | Add PII redaction before logging |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S21 | PI-4 (Q4) | To Do
User Story | US13.1.2 | F13.1 | E13 | F13.1 | As a compliance officer, every AI answer cites the records it used | GIVEN an AI response WHEN displayed THEN its citations are shown and the interaction is written to the audit log. | CBMS exclusive | Squad C — Resident & AI | Should | 5 | 14 | S22 | PI-4 (Q4) | To Do
Task | T13.1.2.1 | US13.1.2 | E13 | F13.1 | Attach citations to every response |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S22 | PI-4 (Q4) | To Do
Task | T13.1.2.2 | US13.1.2 | E13 | F13.1 | Persist AI interactions with token and latency metrics |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S22 | PI-4 (Q4) | To Do
Task | T13.1.2.3 | US13.1.2 | E13 | F13.1 | Render citations in the UI |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S22 | PI-4 (Q4) | To Do
Task | T13.1.2.4 | US13.1.2 | E13 | F13.1 | Escalate to a support ticket when unsure |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S22 | PI-4 (Q4) | To Do
Feature | F13.2 | E13 | E13 | F13.2 | Resident assistant and staff copilots | The conversational surfaces, grounded strictly in tenant data. | CBMS exclusive | Squad C — Resident & AI | Should | 16 | 39 |  | PI-4 (Q4) | To Do
User Story | US13.2.1 | F13.2 | E13 | F13.2 | As a resident, I can ask in Taglish how to get a clearance | GIVEN a question WHEN answered THEN the reply uses only this barangay's fees and requirements, with citations. | CBMS exclusive | Squad C — Resident & AI | Should | 8 | 19 | S22 | PI-4 (Q4) | To Do
Task | T13.2.1.1 | US13.2.1 | E13 | F13.2 | Build the retrieval layer over tenant records |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S22 | PI-4 (Q4) | To Do
Task | T13.2.1.2 | US13.2.1 | E13 | F13.2 | Constrain answers to the caller's RBAC view |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S22 | PI-4 (Q4) | To Do
Task | T13.2.1.3 | US13.2.1 | E13 | F13.2 | Build the resident chat UI |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S22 | PI-4 (Q4) | To Do
Task | T13.2.1.4 | US13.2.1 | E13 | F13.2 | Handle the no-answer case with a ticket offer |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S22 | PI-4 (Q4) | To Do
User Story | US13.2.2 | F13.2 | E13 | F13.2 | As a secretary, the copilot drafts documents and summarises cases | GIVEN a case or request WHEN I ask for a draft THEN a reviewable draft is produced and marked as unsigned. | CBMS exclusive | Squad C — Resident & AI | Should | 8 | 20 | S23 | PI-4 (Q4) | To Do
Task | T13.2.2.1 | US13.2.2 | E13 | F13.2 | Implement certificate and letter drafting |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S23 | PI-4 (Q4) | To Do
Task | T13.2.2.2 | US13.2.2 | E13 | F13.2 | Implement KP case summarisation |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S23 | PI-4 (Q4) | To Do
Task | T13.2.2.3 | US13.2.2 | E13 | F13.2 | Implement report narrative generation |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S23 | PI-4 (Q4) | To Do
Task | T13.2.2.4 | US13.2.2 | E13 | F13.2 | Build the copilot panel in the console |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S23 | PI-4 (Q4) | To Do
Feature | F13.3 | E13 | E13 | F13.3 | Agentic workflow and oversight | A state machine with a hard human gate, plus background integrity sweeps. | CBMS exclusive | Squad C — Resident & AI | Should | 13 | 40 |  | PI-4 (Q4) | To Do
User Story | US13.3.1 | F13.3 | E13 | F13.3 | As a Punong Barangay, an agent can prepare an issuance but never sign it | GIVEN the workflow WHEN it reaches approval THEN it pauses for a named official and every step is inspectable. | CBMS exclusive | Squad C — Resident & AI | Should | 8 | 23 | S23 | PI-4 (Q4) | To Do
Task | T13.3.1.1 | US13.3.1 | E13 | F13.3 | Model workflow runs and steps |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S23 | PI-4 (Q4) | To Do
Task | T13.3.1.2 | US13.3.1 | E13 | F13.3 | Implement verify, blockers, draft, gate and issue steps |  | CBMS exclusive | Squad C — Resident & AI |  |  | 7 | S23 | PI-4 (Q4) | To Do
Task | T13.3.1.3 | US13.3.1 | E13 | F13.3 | Enforce the human gate before issuance |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S23 | PI-4 (Q4) | To Do
Task | T13.3.1.4 | US13.3.1 | E13 | F13.3 | Build the run inspector UI |  | CBMS exclusive | Squad C — Resident & AI |  |  | 6 | S23 | PI-4 (Q4) | To Do
Task | T13.3.1.5 | US13.3.1 | E13 | F13.3 | Unit-test that the gate precedes issuance |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S23 | PI-4 (Q4) | To Do
User Story | US13.3.2 | F13.3 | E13 | F13.3 | As an auditor, background agents flag anomalies for review | GIVEN nightly sweeps WHEN anomalies are found THEN duplicate accounts, disbursement outliers and dormant wallets are reported. | CBMS exclusive | Squad C — Resident & AI | Should | 5 | 17 | S24 | PI-4 (Q4) | To Do
Task | T13.3.2.1 | US13.3.2 | E13 | F13.3 | Implement the duplicate and ghost-account sweep |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S24 | PI-4 (Q4) | To Do
Task | T13.3.2.2 | US13.3.2 | E13 | F13.3 | Implement disbursement anomaly detection |  | CBMS exclusive | Squad C — Resident & AI |  |  | 5 | S24 | PI-4 (Q4) | To Do
Task | T13.3.2.3 | US13.3.2 | E13 | F13.3 | Implement the dormant-wallet report |  | CBMS exclusive | Squad C — Resident & AI |  |  | 3 | S24 | PI-4 (Q4) | To Do
Task | T13.3.2.4 | US13.3.2 | E13 | F13.3 | Surface findings in the console |  | CBMS exclusive | Squad C — Resident & AI |  |  | 4 | S24 | PI-4 (Q4) | To Do
Epic | E14 |  | E14 |  | LGU Hub, Reporting & Public Transparency | The city/DILG view, statutory reporting, and the public barangay website. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 27 | 81 |  | PI-4 (Q4) | To Do |  | Where adoption is actually measured.
Feature | F14.1 | E14 | E14 | F14.1 | Adoption scorecard and hub dashboards | Registration, active usage, merchant density and the cash-out watchdog. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 8 | 24 |  | PI-4 (Q4) | To Do
User Story | US14.1.1 | F14.1 | E14 | F14.1 | As an LGU administrator, I can compare adoption across all my barangays | GIVEN the scorecard WHEN opened THEN each barangay shows registration %, 30-day active %, merchants, cash points and satisfaction against targets. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 8 | 24 | S22 | PI-4 (Q4) | To Do
Task | T14.1.1.1 | US14.1.1 | E14 | F14.1 | Implement the cross-barangay aggregation endpoint |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 6 | S22 | PI-4 (Q4) | To Do
Task | T14.1.1.2 | US14.1.1 | E14 | F14.1 | Compute the cash-out-only watchdog ratio |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 4 | S22 | PI-4 (Q4) | To Do
Task | T14.1.1.3 | US14.1.1 | E14 | F14.1 | Build the sortable scorecard table with target colouring |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 8 | S22 | PI-4 (Q4) | To Do
Task | T14.1.1.4 | US14.1.1 | E14 | F14.1 | Build the hub dashboard with rankings |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 6 | S22 | PI-4 (Q4) | To Do
Feature | F14.2 | E14 | E14 | F14.2 | Statutory and management reporting | Quarterly rollups aligned to NBOO reporting, plus the CSM measure. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 8 | 21 |  | PI-4 (Q4) | To Do
User Story | US14.2.1 | F14.2 | E14 | F14.2 | As a DILG viewer, I can pull a quarterly statistical rollup | GIVEN a quarter WHEN generated THEN registered inhabitants, certificates, KP cases, concerns and disbursements are reported in aggregate only. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 5 | 13 | S23 | PI-4 (Q4) | To Do
Task | T14.2.1.1 | US14.2.1 | E14 | F14.2 | Implement the quarterly aggregation |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 5 | S23 | PI-4 (Q4) | To Do
Task | T14.2.1.2 | US14.2.1 | E14 | F14.2 | Build the report view and CSV export |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 5 | S23 | PI-4 (Q4) | To Do
Task | T14.2.1.3 | US14.2.1 | E14 | F14.2 | Verify the DILG role cannot reach raw PII |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 3 | S23 | PI-4 (Q4) | To Do
User Story | US14.2.2 | F14.2 | E14 | F14.2 | As a manager, I can see our client satisfaction measurement | GIVEN feedback WHEN summarised THEN average rating, satisfaction rate, distribution and grievances display by service. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 3 | 8 | S23 | PI-4 (Q4) | To Do
Task | T14.2.2.1 | US14.2.2 | E14 | F14.2 | Implement the CSM aggregation |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 4 | S23 | PI-4 (Q4) | To Do
Task | T14.2.2.2 | US14.2.2 | E14 | F14.2 | Build the distribution chart without a chart library |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 4 | S23 | PI-4 (Q4) | To Do
Feature | F14.3 | E14 | E14 | F14.3 | Public barangay website | An anti-fixer transparency surface anyone can read without an account. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 11 | 36 |  | PI-4 (Q4) | To Do
User Story | US14.3.1 | F14.3 | E14 | F14.3 | As a citizen, I can see fees, requirements, budget and projects without logging in | GIVEN a barangay page WHEN opened THEN services with fees, the transparency board, ordinances and officials render publicly. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 8 | 26 | S24 | PI-4 (Q4) | To Do
Task | T14.3.1.1 | US14.3.1 | E14 | F14.3 | Implement the public barangay payload endpoint |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 5 | S24 | PI-4 (Q4) | To Do
Task | T14.3.1.2 | US14.3.1 | E14 | F14.3 | Build the site with per-barangay branding |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 8 | S24 | PI-4 (Q4) | To Do
Task | T14.3.1.3 | US14.3.1 | E14 | F14.3 | Build the transparency board (budget, projects, fees) |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 6 | S24 | PI-4 (Q4) | To Do
Task | T14.3.1.4 | US14.3.1 | E14 | F14.3 | Build the privacy-safe 311 heat map |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 5 | S24 | PI-4 (Q4) | To Do
Task | T14.3.1.5 | US14.3.1 | E14 | F14.3 | Add the Full Disclosure Policy notice |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 2 | S24 | PI-4 (Q4) | To Do
User Story | US14.3.2 | F14.3 | E14 | F14.3 | As a content editor, I can manage pages and posts for my barangay | GIVEN the CMS WHEN I publish a post THEN it appears on the public site immediately. | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | Must | 3 | 10 | S24 | PI-4 (Q4) | To Do
Task | T14.3.2.1 | US14.3.2 | E14 | F14.3 | Build CMS pages and posts CRUD |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 5 | S24 | PI-4 (Q4) | To Do
Task | T14.3.2.2 | US14.3.2 | E14 | F14.3 | Build the editor screens with publish toggles |  | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI |  |  | 5 | S24 | PI-4 (Q4) | To Do
Epic | E15 |  | E15 |  | LGUSS-BIMS Interoperability & Compliance Alignment | The companion-mode contract with DILG's mandated system of record. | Integration | Platform | Must | 16 | 51 |  | PI-4 (Q4) | To Do |  | No public BIMS API exists; built as a seam pending a DILG data-sharing agreement.
Feature | F15.1 | E15 | E15 | F15.1 | BIMS adapter and companion mode | Read-from-BIMS provenance, conflict policy and sync visibility. | Integration | Platform | Must | 11 | 28 |  | PI-4 (Q4) | To Do
User Story | US15.1.1 | F15.1 | E15 | F15.1 | As an architect, CBMS defers to BIMS as the system of record | GIVEN companion mode WHEN a BIMS-sourced record is shown THEN it is marked read-only and CBMS never overwrites it. | Integration | Platform | Must | 5 | 14 | S24 | PI-4 (Q4) | To Do
Task | T15.1.1.1 | US15.1.1 | E15 | F15.1 | Define the BimsGateway interface |  | Integration | Platform |  |  | 4 | S24 | PI-4 (Q4) | To Do
Task | T15.1.1.2 | US15.1.1 | E15 | F15.1 | Implement the mock gateway declaring no authorization |  | Integration | Platform |  |  | 4 | S24 | PI-4 (Q4) | To Do
Task | T15.1.1.3 | US15.1.1 | E15 | F15.1 | Add source provenance badges across screens |  | Integration | Platform |  |  | 3 | S24 | PI-4 (Q4) | To Do
Task | T15.1.1.4 | US15.1.1 | E15 | F15.1 | Implement BIMS-wins conflict resolution |  | Integration | Platform |  |  | 3 | S24 | PI-4 (Q4) | To Do
User Story | US15.1.2 | F15.1 | E15 | F15.1 | As an administrator, I can see sync status and outstanding conflicts | GIVEN sync runs WHEN I open the status screen THEN last sync, rows pulled and conflicts display per dataset. | Integration | Platform | Must | 3 | 8 | S25 | PI-4 (Q4) | To Do
Task | T15.1.2.1 | US15.1.2 | E15 | F15.1 | Model sync runs per dataset |  | Integration | Platform |  |  | 2 | S25 | PI-4 (Q4) | To Do
Task | T15.1.2.2 | US15.1.2 | E15 | F15.1 | Build the sync status screen |  | Integration | Platform |  |  | 5 | S25 | PI-4 (Q4) | To Do
Task | T15.1.2.3 | US15.1.2 | E15 | F15.1 | State plainly that no live DILG interface exists |  | Integration | Platform |  |  | 1 | S25 | PI-4 (Q4) | To Do
User Story | US15.1.3 | F15.1 | E15 | F15.1 | As a compliance lead, PhilSys numbers are validated before use | GIVEN a PhilSys number WHEN entered THEN format is validated and normalised, with verification clearly marked as mocked. | Integration | Platform | Must | 3 | 6 | S25 | PI-4 (Q4) | To Do
Task | T15.1.3.1 | US15.1.3 | E15 | F15.1 | Implement PCN format validation and normalisation |  | Integration | Platform |  |  | 3 | S25 | PI-4 (Q4) | To Do
Task | T15.1.3.2 | US15.1.3 | E15 | F15.1 | Implement the mock verification endpoint |  | Integration | Platform |  |  | 2 | S25 | PI-4 (Q4) | To Do
Task | T15.1.3.3 | US15.1.3 | E15 | F15.1 | Label mock status in the UI |  | Integration | Platform |  |  | 1 | S25 | PI-4 (Q4) | To Do
Feature | F15.2 | E15 | E15 | F15.2 | Regulatory documentation pack | The artifacts a government reviewer will actually ask for. | Integration | Platform | Must | 5 | 23 |  | PI-4 (Q4) | To Do
User Story | US15.2.1 | F15.2 | E15 | F15.2 | As a DPO, we hold a privacy impact assessment and NPC registration pack | GIVEN the compliance pack WHEN reviewed THEN PIA, data flows, retention and breach procedures are documented. | Integration | Platform | Must | 5 | 23 | S25 | PI-4 (Q4) | To Do
Task | T15.2.1.1 | US15.2.1 | E15 | F15.2 | Draft the privacy impact assessment |  | Integration | Platform |  |  | 8 | S25 | PI-4 (Q4) | To Do
Task | T15.2.1.2 | US15.2.1 | E15 | F15.2 | Document data flows and retention policy |  | Integration | Platform |  |  | 6 | S25 | PI-4 (Q4) | To Do
Task | T15.2.1.3 | US15.2.1 | E15 | F15.2 | Draft the breach response procedure |  | Integration | Platform |  |  | 4 | S25 | PI-4 (Q4) | To Do
Task | T15.2.1.4 | US15.2.1 | E15 | F15.2 | Prepare the DILG data-sharing agreement request |  | Integration | Platform |  |  | 5 | S25 | PI-4 (Q4) | To Do
Epic | E16 |  | E16 |  | Quality, Security Hardening & Pilot Release | Proving the system rather than asserting it, and getting it live in pilot barangays. | Platform | Platform | Must | 44 | 140 |  | PI-4 (Q4) | To Do |  | Runs continuously; concentrated in PI-4 for release readiness.
Feature | F16.1 | E16 | E16 | F16.1 | Automated test suite | Unit, integration and end-to-end coverage of the flows that matter. | Platform | Platform | Must | 18 | 50 |  | PI-4 (Q4) | To Do
User Story | US16.1.1 | F16.1 | E16 | F16.1 | As a team, critical logic is unit-tested | GIVEN the suite WHEN it runs THEN money math, KP deadlines, RBAC guards and dedupe are covered and green. | Platform | Platform | Must | 5 | 14 | S06 | PI-4 (Q4) | To Do
Task | T16.1.1.1 | US16.1.1 | E16 | F16.1 | Test money conversion, splitting and fees |  | Platform | Platform |  |  | 4 | S06 | PI-4 (Q4) | To Do
Task | T16.1.1.2 | US16.1.1 | E16 | F16.1 | Test the KP deadline engine at each boundary |  | Platform | Platform |  |  | 4 | S06 | PI-4 (Q4) | To Do
Task | T16.1.1.3 | US16.1.1 | E16 | F16.1 | Test every role's permission boundary |  | Platform | Platform |  |  | 4 | S06 | PI-4 (Q4) | To Do
Task | T16.1.1.4 | US16.1.1 | E16 | F16.1 | Wire the suite into CI |  | Platform | Platform |  |  | 2 | S06 | PI-4 (Q4) | To Do
User Story | US16.1.2 | F16.1 | E16 | F16.1 | As a security lead, tenant isolation is proven, not assumed | GIVEN the smoke suite WHEN run against a seeded API THEN cross-tenant reads, VAWC visibility and maker–checker are all asserted. | Platform | Platform | Must | 5 | 14 | S12 | PI-4 (Q4) | To Do
Task | T16.1.2.1 | US16.1.2 | E16 | F16.1 | Build the API smoke harness with real logins |  | Platform | Platform |  |  | 5 | S12 | PI-4 (Q4) | To Do
Task | T16.1.2.2 | US16.1.2 | E16 | F16.1 | Assert cross-tenant isolation on list endpoints |  | Platform | Platform |  |  | 3 | S12 | PI-4 (Q4) | To Do
Task | T16.1.2.3 | US16.1.2 | E16 | F16.1 | Assert maker–checker and VAWC confidentiality |  | Platform | Platform |  |  | 4 | S12 | PI-4 (Q4) | To Do
Task | T16.1.2.4 | US16.1.2 | E16 | F16.1 | Assert DILG aggregate-only access |  | Platform | Platform |  |  | 2 | S12 | PI-4 (Q4) | To Do
User Story | US16.1.3 | F16.1 | E16 | F16.1 | As a team, the flagship journeys are covered end to end | GIVEN Playwright specs WHEN they run THEN certificate issuance, disbursement and 311 pass headlessly. | Platform | Platform | Must | 8 | 22 | S25 | PI-4 (Q4) | To Do
Task | T16.1.3.1 | US16.1.3 | E16 | F16.1 | Set up Playwright with seeded fixtures |  | Platform | Platform |  |  | 5 | S25 | PI-4 (Q4) | To Do
Task | T16.1.3.2 | US16.1.3 | E16 | F16.1 | Write the certificate end-to-end spec |  | Platform | Platform |  |  | 5 | S25 | PI-4 (Q4) | To Do
Task | T16.1.3.3 | US16.1.3 | E16 | F16.1 | Write the disbursement batch spec |  | Platform | Platform |  |  | 5 | S25 | PI-4 (Q4) | To Do
Task | T16.1.3.4 | US16.1.3 | E16 | F16.1 | Write the 311 concern spec |  | Platform | Platform |  |  | 4 | S25 | PI-4 (Q4) | To Do
Task | T16.1.3.5 | US16.1.3 | E16 | F16.1 | Run E2E in CI nightly |  | Platform | Platform |  |  | 3 | S25 | PI-4 (Q4) | To Do
Feature | F16.2 | E16 | E16 | F16.2 | Security hardening and performance | Penetration testing, rate limiting and load validation before go-live. | Platform | Platform | Must | 13 | 37 |  | PI-4 (Q4) | To Do
User Story | US16.2.1 | F16.2 | E16 | F16.2 | As a security lead, the platform passes an OWASP-focused review | GIVEN a security review WHEN completed THEN injection, access control, secrets and transport findings are remediated. | Platform | Platform | Must | 8 | 24 | S26 | PI-4 (Q4) | To Do
Task | T16.2.1.1 | US16.2.1 | E16 | F16.2 | Run dependency and secret scanning |  | Platform | Platform |  |  | 4 | S26 | PI-4 (Q4) | To Do
Task | T16.2.1.2 | US16.2.1 | E16 | F16.2 | Conduct an OWASP Top 10 review |  | Platform | Platform |  |  | 8 | S26 | PI-4 (Q4) | To Do
Task | T16.2.1.3 | US16.2.1 | E16 | F16.2 | Add rate limiting and brute-force protection |  | Platform | Platform |  |  | 4 | S26 | PI-4 (Q4) | To Do
Task | T16.2.1.4 | US16.2.1 | E16 | F16.2 | Remediate findings and retest |  | Platform | Platform |  |  | 8 | S26 | PI-4 (Q4) | To Do
User Story | US16.2.2 | F16.2 | E16 | F16.2 | As an operator, the system performs at pilot scale | GIVEN load tests at pilot volume WHEN run THEN response times stay within target and no query regresses. | Platform | Platform | Must | 5 | 13 | S26 | PI-4 (Q4) | To Do
Task | T16.2.2.1 | US16.2.2 | E16 | F16.2 | Define performance targets |  | Platform | Platform |  |  | 2 | S26 | PI-4 (Q4) | To Do
Task | T16.2.2.2 | US16.2.2 | E16 | F16.2 | Build load test scenarios |  | Platform | Platform |  |  | 5 | S26 | PI-4 (Q4) | To Do
Task | T16.2.2.3 | US16.2.2 | E16 | F16.2 | Profile and index slow queries |  | Platform | Platform |  |  | 6 | S26 | PI-4 (Q4) | To Do
Feature | F16.3 | E16 | E16 | F16.3 | Pilot deployment and enablement | Getting real barangays live, with the training and support to sustain it. | Platform | Platform | Must | 13 | 53 |  | PI-4 (Q4) | To Do
User Story | US16.3.1 | F16.3 | E16 | F16.3 | As a deployment lead, I can onboard a pilot barangay in a day | GIVEN a new barangay WHEN onboarded THEN registration, approval, officials, users and MFA enrolment complete within a day. | Platform | Platform | Must | 5 | 15 | S26 | PI-4 (Q4) | To Do
Task | T16.3.1.1 | US16.3.1 | E16 | F16.3 | Build the barangay onboarding and approval flow |  | Platform | Platform |  |  | 5 | S26 | PI-4 (Q4) | To Do
Task | T16.3.1.2 | US16.3.1 | E16 | F16.3 | Write the deployment runbook |  | Platform | Platform |  |  | 5 | S26 | PI-4 (Q4) | To Do
Task | T16.3.1.3 | US16.3.1 | E16 | F16.3 | Prepare the data migration template |  | Platform | Platform |  |  | 5 | S26 | PI-4 (Q4) | To Do
User Story | US16.3.2 | F16.3 | E16 | F16.3 | As a barangay official, I am trained and supported after go-live | GIVEN go-live WHEN staff need help THEN training materials, a user manual and an in-app ticket channel are available. | Platform | Platform | Must | 5 | 29 | S26 | PI-4 (Q4) | To Do
Task | T16.3.2.1 | US16.3.2 | E16 | F16.3 | Produce role-based training materials |  | Platform | Platform |  |  | 8 | S26 | PI-4 (Q4) | To Do
Task | T16.3.2.2 | US16.3.2 | E16 | F16.3 | Write the user manual in Filipino and English |  | Platform | Platform |  |  | 10 | S26 | PI-4 (Q4) | To Do
Task | T16.3.2.3 | US16.3.2 | E16 | F16.3 | Build the in-app support ticket module |  | Platform | Platform |  |  | 5 | S26 | PI-4 (Q4) | To Do
Task | T16.3.2.4 | US16.3.2 | E16 | F16.3 | Run the train-the-trainer session |  | Platform | Platform |  |  | 6 | S26 | PI-4 (Q4) | To Do
User Story | US16.3.3 | F16.3 | E16 | F16.3 | As a product owner, we can demonstrate the whole system credibly | GIVEN the demo script WHEN followed from a fresh seed THEN every flagship journey works without manual repair. | Platform | Platform | Must | 3 | 9 | S26 | PI-4 (Q4) | To Do
Task | T16.3.3.1 | US16.3.3 | E16 | F16.3 | Write and rehearse the demo script |  | Platform | Platform |  |  | 5 | S26 | PI-4 (Q4) | To Do
Task | T16.3.3.2 | US16.3.3 | E16 | F16.3 | Verify the script against a fresh seed |  | Platform | Platform |  |  | 4 | S26 | PI-4 (Q4) | To Do

## Epic Summary
Epic Summary — scope and effort rollup
Every figure is a formula over the Backlog sheet. Nothing here is hardcoded.
Epic ID | Epic | Group | Squad | PI | MoSCoW | Features | User Stories | Tasks | Story Points | Est. Hours | % of Total Points
E01 | Platform Foundation & Multi-Tenancy | Platform | Platform | PI-1 (Q1) | Must | 3 | 7 | 31 | 45 | 129 | 9.128%
E02 | Identity, Access & Security Baseline | Platform | Platform | PI-1 (Q1) | Must | 3 | 9 | 33 | 44 | 112 | 8.925%
E03 | Resident Registry — BIPS Parity | BIMS-parity: BIPS | Squad A — Registry & Services | PI-1 (Q1) | Must | 3 | 5 | 18 | 24 | 70 | 4.868%
E04 | Service Issuance — BCIS Parity | BIMS-parity: BCIS | Squad A — Registry & Services | PI-2 (Q2) | Must | 3 | 7 | 25 | 34 | 89 | 6.897%
E05 | Financial Management — BFMS Parity | BIMS-parity: BFMS | Squad B — Money | PI-2 (Q2) | Must | 2 | 3 | 12 | 18 | 51 | 3.651%
E06 | Barangay E-Wallet — Core Rails | CBMS exclusive | Squad B — Money | PI-2 (Q2) | Must | 3 | 8 | 31 | 44 | 116 | 8.925%
E07 | Agent & Merchant Network (CICO) | CBMS exclusive | Squad B — Money | PI-2 (Q2) | Must | 2 | 3 | 11 | 18 | 47 | 3.651%
E08 | Justice & Safety — KPISBH Parity | BIMS-parity: KPISBH | Squad A — Registry & Services | PI-3 (Q3) | Must | 2 | 5 | 18 | 29 | 69 | 5.882%
E09 | Assets & Disaster Resilience — BAMS / BDRIS Parity | BIMS-parity: BAMS, BDRIS | Squad A — Registry & Services | PI-3 (Q3) | Should | 2 | 5 | 16 | 24 | 69 | 4.868%
E10 | Resident Self-Service Suite | CBMS exclusive | Squad C — Resident & AI | PI-3 (Q3) | Must | 4 | 9 | 35 | 49 | 153 | 9.939%
E11 | Health, Social Services & Livelihood | Mixed — new capability | Squad C — Resident & AI | PI-3 (Q3) | Should | 2 | 4 | 13 | 20 | 58 | 4.057%
E12 | Governance & Legislative — BORIS / BDP / BBI / BGADPBMS | BIMS-parity: BORIS, BDP, BBI, BGADPBMS | Squad A — Registry & Services | PI-4 (Q4) | Should | 4 | 4 | 14 | 18 | 55 | 3.651%
E13 | AI Agentic Layer | CBMS exclusive | Squad C — Resident & AI | PI-4 (Q4) | Should | 3 | 6 | 25 | 39 | 108 | 7.911%
E14 | LGU Hub, Reporting & Public Transparency | Mixed — BIMS Website parity + exclusive | Squad C — Resident & AI | PI-4 (Q4) | Must | 3 | 5 | 16 | 27 | 81 | 5.477%
E15 | LGUSS-BIMS Interoperability & Compliance Alignment | Integration | Platform | PI-4 (Q4) | Must | 2 | 4 | 14 | 16 | 51 | 3.245%
E16 | Quality, Security Hardening & Pilot Release | Platform | Platform | PI-4 (Q4) | Must | 3 | 8 | 29 | 44 | 140 | 8.925%
| TOTAL |  |  |  |  | 44 | 92 | 341 | 493 | 1398 | 100%
Assumption: story points are Fibonacci estimates made at backlog-definition time and should be re-estimated at sprint planning. Task hours are indicative engineering effort, excluding meetings, leave and support load. Source: CBMS build specification (OPUS-BUILD-PROMPT.md).

## Sprint Plan
Sprint Plan — 26 two-week sprints
Planned points and hours are formulas reading the Backlog. Adjust Capacity to model a different team size.
Sprint | PI | Start (Mon) | End (Fri) | Focus | Planned Points | Planned Hours | Stories | Capacity (pts) | Load vs Capacity
S01 | PI-1 (Q1) | 2026-01-05 | 2026-01-16 | Monorepo, schema and local environment stood up | 18 | 54 | 2 | 20 | 90%
S02 | PI-1 (Q1) | 2026-01-19 | 2026-01-30 | CI/CD, shared packages, tenancy scaffolding | 8 | 22 | 2 | 12 | 66.67%
S03 | PI-1 (Q1) | 2026-02-02 | 2026-02-13 | Tenant scoping, money primitives, authentication | 21 | 58 | 4 | 22 | 95.45%
S04 | PI-1 (Q1) | 2026-02-16 | 2026-02-27 | RBAC model, audit trail, seed data | 21 | 56 | 3 | 26 | 80.77%
S05 | PI-1 (Q1) | 2026-03-02 | 2026-03-13 | Registry: households and inhabitants; MFA reset | 21 | 58 | 4 | 26 | 80.77%
S06 | PI-1 (Q1) | 2026-03-16 | 2026-03-27 | Dedupe, consent registry, encryption, unit tests | 26 | 69 | 6 | 26 | 100%
S07 | PI-2 (Q2) | 2026-03-30 | 2026-04-10 | Certificate catalog, fee schedule, RBI export | 8 | 23 | 2 | 26 | 30.77%
S08 | PI-2 (Q2) | 2026-04-13 | 2026-04-24 | Budget model, EMI provider seam, request intake | 18 | 47 | 3 | 26 | 69.23%
S09 | PI-2 (Q2) | 2026-04-27 | 2026-05-08 | Wallet provisioning, fee payment, ledger posting | 26 | 72 | 4 | 26 | 100%
S10 | PI-2 (Q2) | 2026-05-11 | 2026-05-22 | Disbursement batch builder, document rendering, verification | 19 | 46 | 4 | 26 | 73.08%
S11 | PI-2 (Q2) | 2026-05-25 | 2026-06-05 | Maker–checker execution, OTC fallback, SER report | 18 | 48 | 4 | 26 | 69.23%
S12 | PI-2 (Q2) | 2026-06-08 | 2026-06-19 | Bills and merchant QR, agent cash-out, smoke suite | 23 | 65 | 4 | 26 | 88.46%
S13 | PI-2 (Q2) | 2026-06-22 | 2026-07-03 | Agent liquidity and hub rebalancing | 10 | 24 | 2 | 26 | 38.46%
S14 | PI-3 (Q3) | 2026-07-06 | 2026-07-17 | Blotter and VAWC restriction; resident app shell | 15 | 39 | 3 | 26 | 57.69%
S15 | PI-3 (Q3) | 2026-07-20 | 2026-07-31 | KP deadline engine and stage flow; 311 concerns | 21 | 61 | 3 | 26 | 80.77%
S16 | PI-3 (Q3) | 2026-08-03 | 2026-08-14 | KP deadline watch, property register, SOS | 19 | 52 | 4 | 26 | 73.08%
S17 | PI-3 (Q3) | 2026-08-17 | 2026-08-28 | Hazards, evacuation centres, disaster event mode | 13 | 38 | 2 | 26 | 50%
S18 | PI-3 (Q3) | 2026-08-31 | 2026-09-11 | Vulnerable registry, offline sync, health campaigns | 21 | 63 | 4 | 26 | 80.77%
S19 | PI-3 (Q3) | 2026-09-14 | 2026-09-25 | Appointments, feedback/CSM, digital ID, health booking | 18 | 52 | 4 | 26 | 69.23%
S20 | PI-4 (Q4) | 2026-09-28 | 2026-10-09 | Participatory budgeting, announcements, jobs and benefits | 20 | 60 | 4 | 26 | 76.92%
S21 | PI-4 (Q4) | 2026-10-12 | 2026-10-23 | Legislation, development plan, GAD, institutions; AI platform | 18 | 54 | 4 | 26 | 69.23%
S22 | PI-4 (Q4) | 2026-10-26 | 2026-11-06 | Resident assistant, AI citations, adoption scorecard | 21 | 57 | 3 | 26 | 80.77%
S23 | PI-4 (Q4) | 2026-11-09 | 2026-11-20 | Staff copilots, agentic workflow, quarterly and CSM reporting | 24 | 64 | 4 | 26 | 92.31%
S24 | PI-4 (Q4) | 2026-11-23 | 2026-12-04 | Oversight agents, public website, CMS, BIMS adapter | 21 | 67 | 4 | 26 | 80.77%
S25 | PI-4 (Q4) | 2026-12-07 | 2026-12-18 | Sync status, PhilSys validation, compliance pack, E2E suite | 19 | 59 | 4 | 26 | 73.08%
S26 | PI-4 (Q4) | 2026-12-21 | 2027-01-01 | Security hardening, performance, pilot onboarding and enablement | 26 | 90 | 5 | 28 | 92.86%
|  |  |  | TOTAL | 493 | 1398 | 92 | 654 | 75.38%
Capacity (blue) is a planning input — change it to model a different team size and every load figure recalculates.
Calibration: 1 story point ≈ 2.8 hours of focused engineering in these estimates. The plan runs at roughly 75% load, and red in 'Load vs Capacity' marks a sprint to rebalance at planning.
IMPORTANT — why backlog hours are far below total team hours: this backlog sizes DEFINED PRODUCT SCOPE only. It deliberately excludes discovery, rework, code review, ceremonies, environment issues, production support, field deployment, training and the barangay-by-barangay rollout — which in a government programme of this kind consume the majority of a team's year. Do not read total task hours as total team effort, and do not use this sheet on its own to size the team.

## Release Roadmap
Release Roadmap — four program increments
What a stakeholder can see working at the end of each quarter.
PI | Quarter | Sprints | Theme | Epics delivered | Story Points | Stories | Milestone / Release Goal
PI-1 (Q1) | Q1 | S01–S06 | Foundation and the resident registry | E01 Platform · E02 Identity & Security · E03 Registry (BIPS) · E16 Quality (start) | 113 | 21 | Internal milestone: a barangay can be onboarded, staff sign in with MFA, and residents and households can be registered with consent on file.
PI-2 (Q2) | Q2 | S07–S13 | Services and money | E04 Issuance (BCIS) · E05 Finance (BFMS) · E06 E-Wallet · E07 Agent network | 114 | 21 | First demonstrable end-to-end value: a resident requests and pays for a clearance, the Punong Barangay approves it, and a disbursement batch pays 60 people with maker–checker and a reconciled ledger.
PI-3 (Q3) | Q3 | S14–S19 | Field operations and the resident app | E08 Justice & Safety (KPISBH) · E09 Assets & Disaster (BAMS/BDRIS) · E10 Resident self-service · E11 Health & Livelihood | 122 | 23 | Pilot-ready for daily operations: KP cases run against the statutory clock, a disaster event can be run end to end, and residents can report concerns, raise SOS and book appointments.
PI-4 (Q4) | Q4 | S20–S26 | Governance, intelligence and pilot go-live | E12 Governance · E13 AI layer · E14 Hub & Transparency · E15 BIMS interoperability · E16 Hardening | 144 | 27 | Pilot release: the public transparency site is live, the LGU hub reports adoption against target, the AI layer assists with a human approval gate, and the security and privacy pack is complete.
|  |  |  | TOTAL | 493 | 92

## Team & Capacity
Team & Capacity assumptions
The delivery team the sprint capacity figures assume. Headcount is a planning input (blue).
Role | Headcount | Squad | Primary epics | Notes
Chief Technology Officer | 1 | Platform | All | Architecture ownership and technical governance.
Project Manager | 1 | Platform | All | Delivery, ceremonies, stakeholder reporting.
Solution Architect | 1 | Platform | E01, E15 | Data model, tenancy, BIMS interoperability design.
Development Lead | 1 | Platform | All | Code quality, review throughput, technical mentoring.
Backend Developer | 3 | Split across squads | E01–E15 | API, domain logic, database.
Frontend Developer | 2 | Split across squads | E04, E10, E14 | Console and hub web applications.
Mobile Developer | 2 | Squad C — Resident & AI | E10, E07 | Resident and agent PWAs, offline sync.
UI/UX Designer | 1 | Shared | E10, E14 | Resident-first design; Filipino/Taglish content design.
QA Engineer | 3 | Split across squads | E16 | Test automation, E2E, release verification.
DevOps / Cloud Engineer | 1 | Platform | E01, E16 | CI/CD, environments, observability.
AI / ML Engineer | 2 | Squad C — Resident & AI | E13 | Agentic layer, retrieval, guardrails.
Cybersecurity Engineer | 1 | Platform | E02, E16 | Threat modelling, hardening, penetration testing.
Product Specialist | 1 | Shared | All | Backlog grooming, acceptance, domain research.
Business Analyst | 1 | Shared | E03, E05, E12 | Process mapping against DILG requirements.
Data Privacy Officer (part-time) | 1 | Shared | E02, E15 | RA 10173 compliance, PIA, NPC registration.
Field / Deployment Lead | 3 | Field & Enablement | E16 | Pilot onboarding, training, on-site support.
Help Desk / Support | 2 | Field & Enablement | E16 | Tier-1 support and ticket triage.
IT Technical Support | 2 | Field & Enablement | E16 | Device, connectivity and hall setup.
TOTAL HEADCOUNT | 29
Assumption: not every role contributes story points. Sprint capacity on the 'Sprint Plan' sheet reflects the engineering roles only (backend, frontend, mobile, AI, DevOps and QA), which is why 29 people plan to roughly 80 points per sprint rather than a higher figure.